## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 11/05/2023 | MS D.PALIT AND CO. | 62.24 | 11.14 | 17.9 | 100
2 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Material Requisition To Resource Division |  |  | RTOR000192/2022-2023 | 109/2/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 65.22 | 0 | 0 | 0
3 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1235/1/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 75.7 | 0 | 0 | 0
4 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Material Requisition To Resource Division |  |  | RTOR000263/2022-2023 | 902/1/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 14.85 | 0 | 0 | 0
5 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Material Requisition To Resource Division |  |  | RTOR000383/2023-2024 | 3058/2/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.85 | 0 | 0 | 0
6 | HOOGHLY | Singur | Electrical | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Quotation for new service connection at Nanda W/S Sch., T/W No. - II, District - Hooghly |  |  | BILL/03889/2023-2024 | 301 | 22/09/2023 | 22/09/2023 | WBSEDCL | 0.64 | 0 | 0 | 0
7 | HOOGHLY | Singur | Electrical | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Quotation for new service connection for Nanda W/s Sch., H/W Site(T/W No.- I), Dist - Hooghly |  |  | BILL/01921/2023-2024 | 88 | 12/07/2023 | 12/07/2023 | WBSEDCL | 7.92 | 0 | 0 | 0
8 | HOOGHLY | Singur | Electrical | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Additional Quotation for Nanda W/S Sch., T/W no. - I, Block - Singur, Dt. - Hooghly |  |  | BILL/02869/2023-2024 | 196 | 17/08/2023 | 17/08/2023 | WBSEDCL | 0.43 | 0 | 0 | 0
9 | HOOGHLY | Singur | Electrical | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nanda water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000165/2022-2023 | 3499/ED | 30/12/2022 | 30/03/2023 | RAJIB COMPANY | 21.48 | 21.45 | 99.86 | 95
10 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 06/08/2023 | OSMAN SEKH | 80.85 | 16.06 | 19.87 | 100
11 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Road Restoration of Anandanagar Health Centre Road |  |  | BILL/01810/2023-2024 | BP-2024-25-2 | 08/04/2024 | 08/04/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 11.11 | 0 | 0 | 0
12 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in NANDA Water Supply Scheme at SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000746/2022-2023 | 682/HUG | 10/03/2023 | 28/08/2025 | PRASUN ENTERPRISE (PRASUN BISWAS) | 614.2 | 328.83 | 53.54 | 85
13 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Sinking of Additional tubewell with Construction of switch-room & boundary wall, Laying Rising Main at Proposed 3rd TW site at Nanda Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000029/2025-2026 | 1174/HUG | 02/05/2025 | 31/07/2025 | PRASUN ENTERPRISE (PRASUN BISWAS) | 30.43 | 0 | 0 | 0
14 | HOOGHLY | Singur | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Laying balance pipeline and other allied works at NANDA PWSS under Chandannagar Sub Division, PHE Dte. Hooghly |  |  | ORD/000030/2025-2026 | 1175/HUG | 02/05/2025 | 01/07/2025 | PRASUN ENTERPRISE (PRASUN BISWAS) | 44.68 | 0 | 0 | 0
15 | HOOGHLY | Singur | Electrical | NANDA PIPED WATER SUPPLY SCHEME | SM/12567 | New | Quotation for new service connection at Nanda W/S Sch., T/W No. - III,[SM/12567], Taherpur Daspara, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref Id. - 503969448, Dt. - 16-05-25, Application No. - 5004742598 |  |  | BILL/01140/2025-2026 |  | 17/06/2025 | 17/06/2025 | WBSEDCL | 7.08 | 0 | 0 | 0
Total | [13 empty] | 1051.68 | 377.49 | 35.89