## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Material Requisition To Resource Division |  |  | RTOR000129/2022-2023 | 2471/Hug | 18/11/2022 | 18/11/2022 | Resource Division | 20.08 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 11/05/2023 | MS D.PALIT AND CO. | 62.24 | 10.89 | 17.49 | 100
3 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Material Requisition To Resource Division |  |  | RTOR000190/2022-2023 | 109/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 102.73 | 0 | 0 | 0
4 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Material Requisition To Resource Division |  |  | RTOR000157/2022-2023 | 01/04/Hug | 02/01/2023 | 02/01/2023 | Resource Division | 20.08 | 0 | 0 | 0
5 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Material Requisition To Resource Division |  |  | RTOR000262/2022-2023 | 902/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 20.08 | 0 | 0 | 0
6 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 1383/33/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 20.08 | 0 | 0 | 0
7 | HOOGHLY | Singur | Electrical | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Quotation Bill for New Service Connection at Atisara W/S. Sch. TW-II |  |  | BILL/04502/2023-2024 | 543 | 19/12/2023 | 19/12/2023 | WBSEDCL | 2.96 | 0 | 0 | 0
8 | HOOGHLY | Singur | Electrical | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Quotation for new service connection at Atisara W/s Sch.,T/W - I, Block - Singur |  |  | BILL/02063/2023-2024 | 115 | 20/07/2023 | 20/07/2023 | WBSEDCL | 5.59 | 0 | 0 | 0
9 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Emergent requirement of rectification of damages caused to road under Hooghly Highway Division II |  |  | BILL/00499/2023-2024 | BP-2023-24-400 | 26/09/2023 | 26/09/2023 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 10.04 | 0 | 0 | 0
10 | HOOGHLY | Singur | Electrical | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Atisara water supply scheme, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000123/2022-2023 | 3479/ED | 30/12/2022 | 30/03/2023 | R.N.S. TRADING | 23.26 | 11.28 | 48.5 | 49
11 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Horizontal Auger boring with water jet system Including Approach road at Atisara W/S Scheme under Chandannagar Sub - Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000757/2023-2024 | 450/HUG | 15/02/2024 | 04/01/2025 | MINTU CHAKRABORTY | 36.19 | 0 | 0 | 2
12 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Sinking of1 No. Additional tube-well , Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for atisara Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. |  |  | ORD/000235/2024-2025 | 3470/HUG | 04/10/2024 | 03/12/2024 | M/S SHIVAM UDYOG | 26.55 | 0 | 0 | 0
13 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 06/08/2023 | OSMAN SEKH | 80.85 | 15.85 | 19.6 | 100
14 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Atisara PWSS, Beraberi PWSS, Barakamplur PWSS, Diara PWSS, Kamarkundu PWSS, Nanda PWSS) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000970/2023-2024 | 299/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
15 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Purusatyampur H/W site & Atisara 2nd T/W Site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000936/2023-2024 | 281/Chan | 15/03/2024 | 30/03/2024 | SUDIPTA SINHA | 0.88 | 0.82 | 93.46 | 100
16 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Approach road at Atisara 2nd Tubewell site under Atisara water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000955/2023-2024 | 293/Chan | 15/03/2024 | 30/03/2024 | AMBIAN INFRASTRUCTURE | 0.94 | 0.94 | 99.98 | 100
17 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main& Interconnection between O.H.R , TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in ATISARA Water Supply Scheme at SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000703/2022-2023 | 404/HUG | 13/02/2023 | 27/05/2026 | MINTU CHAKRABORTY | 769.58 | 608.6 | 79.08 | 97
18 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Laying balance pipeline and other allied works at ATISARA PWSS under Chandannagar Sub Division, PHE Dte. Hooghly |  |  | ORD/000028/2025-2026 | 1173/HUG | 02/05/2025 | 01/07/2025 | MINTU CHAKRABORTY | 33.71 | 0 | 0 | 0
19 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Construction of boundary wall with Gate & Internal Pathway at ATISARA 2nd pump hou se site under Singur Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000269/2025-2026 | 915/CHAN | 21/07/2025 | 10/08/2025 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 5 | 0 | 0 | 0
20 | HOOGHLY | Singur | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME | SM/12727 | New | Construction of road with plinth protection and land development at ATISARA 2nd pump house site under Singur block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000270/2025-2026 | 916/CHAN | 21/07/2025 | 10/08/2025 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 5 | 0 | 0 | 0
Total | [13 empty] | 1246.79 | 649.33 | 52.08