## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/12882 | Retrofitting | Providing 700 nos Functional Household Tap Connection (FHTC) within the command area of GUPTIPARA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000428/2022-2023 | 2363/HUG | 07/11/2022 | 12/12/2022 | ARUN SEAL AND CO. | 41.06 | 41.02 | 99.9 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/12882 | Retrofitting | Providing Functional Household Tap Connection at Roypara ( Mirdanga) village of Guptipara 1 No. Gram Panchyet under Guptipara W/S scheme under Chinsurah Sub- Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000308/2023-2024 | 691/CH | 27/07/2023 | 11/08/2023 | MAA BUNAMATA ENTERPRISE | 0.97 | 0.97 | 100 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/12882 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under BALAGARH Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000345/2023-2024 | 2428/HUG | 11/08/2023 | 10/09/2023 | SB ASSOCIATES | 42.72 | 38.01 | 88.98 | 85
Total | [13 empty] | 84.75 | 80 | 94.4