## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1234/24/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 74.78 | 0 | 0 | 0
2 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Material Requisition To Resource Division |  |  | RTOR000416/2023-2024 | 3057/42/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.17 | 0 | 0 | 0
3 | HOOGHLY | Goghat-I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Quotation of New Service Connection for Kota w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under ED,PHE Dte (SM/13320) Application No-5004009660 Reference Id-503561831 |  |  | BILL/06048/2023-2024 | 742 | 08/02/2024 | 08/02/2024 | WBSEDCL | 3.97 | 0 | 0 | 0
4 | HOOGHLY | Goghat-I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Quotation of New Service Connection for KOTA w/s scheme PH No-2 Block-Goghat-I Dist-Hooghly under ED,PHE Dte. (SM/13320) Application No-5004018773 Reference Id-503565232 |  |  | BILL/06101/2023-2024 | 765 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.68 | 0 | 0 | 0
5 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for KOTA Piped Water Supply Scheme underARAMBAGH Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000245/2024-2025 | 3465/HUG | 04/10/2024 | 01/02/2025 | P. B. ENTERPRISE(PINTU BHADURI) | 53.65 | 14.79 | 27.57 | 50
6 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PUKHURIA PWSS- 3 nos (2) SELAMPUR PWSS (Z-I)- 2 nos (3) SHANTIPUR PWSS (Z-I)- 1 nos (4) KOTA PWSS - 4nos (5) SUNIA PWSS - 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002741/2024-2025 | 1149/Arg | 10/12/2024 | 10/01/2025 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
7 | HOOGHLY | Goghat-I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kota water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000174/2022-2023 | 767/ED | 09/02/2023 | 16/08/2025 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 21.06 | 20.33 | 96.5 | 40
8 | HOOGHLY | Goghat-I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KOTA PIPED W/S SCHEME, T.W. No. III & IV, Block: Goghat-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002505/2023-2024 | 421/ED | 29/02/2024 | 01/09/2025 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0 | 30
9 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Quotation of New Service Connection for Kota w/s Scheme,PH No-III Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte (SM/13320) Application No-5004550599 Reference Id-503849867 |  |  | BILL/01129/2024-2025 | BP-2024-25-752 | 18/03/2025 | 18/03/2025 | WBSEDCL | 4.66 | 0 | 0 | 0
10 | HOOGHLY | Goghat-I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Quotation of New Service Connection for Kota w/s Scheme,PH No-IV Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte (SM/13320) Application No-5004550623 Reference Id-503849821 |  |  | BILL/03077/2024-2025 | 664 | 21/01/2025 | 21/01/2025 | WBSEDCL | 5.58 | 0 | 0 | 0
11 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | GOBINDANAGAR (ZONE-I), KOTA, KUMURSA Piped Water Supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000159/2023-2024 | 1602/HUG | 01/06/2023 | 01/04/2026 | P.B. ENTERPRISE (PINTU BHADURI) | 1078.43 | 292.77 | 27.15 | 70
Total | [13 empty] | 1283.45 | 327.89 | 25.55