## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat - I | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1234/24/Hug | 28/04/2023 |  | Resource Division | 74.78 | 0 | 0 | 0
2 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01121/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 97.65 | 0 | 0 | 0
3 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Goghat water supply scheme, T.W. No.- I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000210/2022-2023 | 837/ED | 14/02/2023 | 15/05/2023 | SUTRADHAR TRADERS | 10.78 | 0 | 0 | 0
4 | HOOGHLY | Goghat - I | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Material Requisition To Resource Division |  |  | RTOR000416/2023-2024 | 3057/42/Hug | 11/10/2023 |  | Resource Division | 14.17 | 0 | 0 | 0
5 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Quotation of New Service Connection for Kota w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under ED,PHE Dte (SM/13320) Application No-5004009660 Reference Id-503561831 |  |  | BILL/06048/2023-2024 | 742 | 08/02/2024 |  | WBSEDCL | 3.97 | 0 | 0 | null
6 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Quotation of New Service Connection for Kota w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under ED,PHE Dte (SM/13320) Application No-5004009660 Reference Id-503561831 |  |  | BILL/06048/2023-2024 | 742 | 08/02/2024 |  | WBSEDCL | 3.97 | 0 | 0 | null
7 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Quotation of New Service Connection for KOTA w/s scheme PH No-2 Block-Goghat-I Dist-Hooghly under ED,PHE Dte. (SM/13320) Application No-5004018773 Reference Id-503565232 |  |  | BILL/06101/2023-2024 | 765 | 16/02/2024 |  | WBSEDCL | 4.68 | 0 | 0 | null
8 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Quotation of New Service Connection for KOTA w/s scheme PH No-2 Block-Goghat-I Dist-Hooghly under ED,PHE Dte. (SM/13320) Application No-5004018773 Reference Id-503565232 |  |  | BILL/06101/2023-2024 | 765 | 16/02/2024 |  | WBSEDCL | 4.68 | 0 | 0 | null
9 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KOTA PIPED W/S SCHEME, T.W. No. III & IV, Block: Goghat-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002505/2023-2024 | 421/ED | 29/02/2024 | 29/05/2024 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0 | 0
10 | HOOGHLY | Goghat - I | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | GOBINDANAGAR (ZONE-I), KOTA, KUMURSA Piped Water Supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000159/2023-2024 | 1602/HUG | 01/06/2023 | 26/05/2024 | P.B. ENTERPRISE (PINTU BHADURI) | 1078.43 | 60.6 | 5.62 | 50
11 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13320 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kota water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000174/2022-2023 | 767/ED | 09/02/2023 | 10/05/2023 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 21.06 | 10.16 | 48.25 | 40
Total | [13 empty] | 1335.65 | 70.76 | 5.3