## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Polba-Dadpur | Hooghly Division | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13321 | New | Material Requisition To Resource Division |  |  | RTOR000224/2023-2024 | 1386/3/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 21.59 | 0 | 0 | 0
2 | HOOGHLY | Polba-Dadpur | Hooghly Division | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13321 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 1264/3/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 12.22 | 0 | 0 | 0
3 | HOOGHLY | Polba-Dadpur | Hooghly Division | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13321 | New | Material Requisition To Resource Division |  |  | RTOR000487/2023-2024 | 3059/20/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 21.59 | 0 | 0 | 0
4 | HOOGHLY | Polba-Dadpur | Electrical | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13321 | New | Quotation Bill for New Service Connection at Ghatampur W/S. Sch. |  |  | BILL/04322/2023-2024 | 430,431,432,433 | 21/11/2023 | 21/11/2023 | WBSEDCL | 15.55 | 0 | 0 | 0
5 | HOOGHLY | Polba-Dadpur | Electrical | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13321 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghatampur water supply scheme, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000185/2022-2023 | 778/ED | 09/02/2023 | 10/05/2023 | C.M.S. ENGINEERING CONCERN | 23.74 | 23.17 | 97.58 | 97
6 | HOOGHLY | Polba-Dadpur | Electrical | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13321 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghatampur water supply scheme, T.W. No. III & IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000878/2023-2024 | 3451/ED | 11/08/2023 | 09/11/2023 | C.M.S. ENGINEERING CONCERN | 23.25 | 22.19 | 95.43 | 97
7 | HOOGHLY | Polba-Dadpur | Hooghly Division | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13321 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 02/09/2025 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 551.22 | 15.01 | 15
Total | [13 empty] | 3790.01 | 596.58 | 15.74