## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13322 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Marakhana water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000189/2022-2023 | 782/ED | 09/02/2023 | 10/05/2023 | S.G. TECHNICAL SERVICES | 20.49 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13322 | New | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 1385/38/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 12.02 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13322 | New | Material Requisition To Resource Division |  |  | RTOR000385/2023-2024 | 3057/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 12.02 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13322 | New | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 1263/1/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 41.15 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13322 | New | Quotation of New Service Connection for Marakhana w/sScheme,Zone-II,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical division,PHE Dte.(SM/13322). Application No-5004325249, Reference Id-503707789 |  |  | BILL/01406/2024-2025 | 350 | 31/07/2024 | 31/07/2024 | WBSEDCL | 7.6 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13322 | New | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-II,Ph No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte.(SM/13322) Application No-5004011194 Reference Id-503561404 |  |  | BILL/06480/2023-2024 | 901 | 19/03/2024 | 19/03/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13322 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 01/01/2026 | MACKINTOSH BURN LIMITED | 5743.06 | 0 | 0 | 50
Total | [13 empty] | 5839.71 | 0 | 0