## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 1385/45/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 8.35 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Material Requisition To Resource Division |  |  | RTOR000414/2023-2024 | 3059/43/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 8.35 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1234/39/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 14.42 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000146/2024-2025 | 1169/ED | 14/06/2024 | 12/09/2024 | GOENKA ENTERPRISE | 10.74 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Quotation money deposition for new service connection at Chingra w/s scheme, Zone- I, T.W. No.-2, Dist.-Hooghly under PHE Dte. Application No- 5004201533 Reference ID- 503652893 SM Code- 13325 |  |  | BILL/00821/2024-2025 | 223 | 18/06/2024 | 18/06/2024 | WBSEDCL | 3.33 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Quotation of New Service Connection for Chinra w/s Scheme,Zone-I,PH No-III Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13325) Application No-5004308863 Reference Id-503700260 |  |  | BILL/02035/2024-2025 | 510 | 21/10/2024 | 21/10/2024 | WBSEDCL | 3.75 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Quotation for Shifting Existing LT Structure at Chinra w/s Scheme,Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13325).Application No-100000121107 Reference Id-860315657 |  |  | BILL/02094/2024-2025 | 548 | 30/10/2024 | 30/10/2024 | WBSEDCL | 0.63 | 0 | 0 | 0
8 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chinra water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Junior Engineer4 | ORD/000184/2022-2023 | 777/ED | 09/02/2023 | 26/07/2025 | GOENKA ENTERPRISE | 20.48 | 10.43 | 50.95 | 10
9 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of Chingra Zone-I Piped Water Supply Scheme under Khanakul-II Block of ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000299/2024-2025 | 3658/HUG | 13/11/2024 | 12/03/2026 | M/S KAUSAR CONSTRUCTION | 16.1 | 0 | 0 | 60
10 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) CHILADANGI PWSS- 2no's (2) PATUL PWSS -1 no's (3) RADHABALLAVPUR PWSS (Z-I)- 1 no's (4) RADHABALLAVPUR PWSS (Z-II)- 2 no's (5) UDAYPUR PWSS - 2no's, (6) UDNA PWSS - 2no's, (7) CHINRA PWSS (Z-I)- 1 no's, (8) CHINRA PWSS (Z-II)- 3 no's | Assistant Engineer | Junior Engineer (Civill) | ORD/002745/2024-2025 | 1153/Arg | 10/12/2024 | 10/01/2025 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
11 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-I, CHINRA (Z-I AND II), ROUTHKHANA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000841/2023-2024 | 721/HUG | 05/03/2024 | 27/08/2025 | SPG ENTERPRISES | 64.23 | 14.27 | 22.21 | 50
12 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13325 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) PALASPAI PWSS (ii) SABALSINGHAPUR PWSS (iii) CHINGRA (ZONE- I) PWSS (iv) CHINGRA (ZONE- II) PWSS (v) HAYATPUR PWSS (vi) PRATAPNAGAR PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000441/2024-2025 | 802/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 152.32 | 24.7 | 16.22