## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-II | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | SM/13333 | New | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 1385/55/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 12.9 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-II | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | SM/13333 | New | Material Requisition To Resource Division |  |  | RTOR000469/2023-2024 | 3057/15/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 12.71 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-II | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | SM/13333 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 1234/43/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 30.64 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-II | Electrical | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | SM/13333 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Mostafapur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002465/2023-2024 | 326/ED | 21/02/2024 | 21/05/2024 | M.S ENTERPRISE | 21.9 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-II | Electrical | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | SM/13333 | New | Quotation of New Service Connection for Mostafapur w/s scheme,TW No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13333) Application No-5004151915 Reference Id-503634018 |  |  | BILL/01590/2024-2025 | 357 | 07/08/2024 | 07/08/2024 | WBSEDCL | 8.49 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-II | Electrical | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | SM/13333 | New | Quotation of New Service Connection for Mostafapur w/s Scheme,PH No-I Block-Khanakul-II District-Hooghly under Electrical Division,PHE Dte.(SM/13333) Application No-5004136071 Reference Id-503627505. |  |  | BILL/00709/2024-2025 | 211 | 11/06/2024 | 11/06/2024 | WBSEDCL | 3.42 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-II | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | SM/13333 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 01/01/2026 | MACKINTOSH BURN LIMITED | 5743.06 | 0 | 0 | 50
8 | HOOGHLY | Khanakul-II | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | SM/13333 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at POL (2Nos.), MOSTAFAPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000222/2024-2025 | 3434/HUG | 03/10/2024 | 28/09/2025 | DIBYENDU DHARA | 47.26 | 0 | 0 | 50
9 | HOOGHLY | Khanakul-II | Electrical | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | SM/13333 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MOSTAFAPUR water supply scheme, TW No. III, Block: Khanakul-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/003097/2024-2025 | 483/ED | 18/03/2025 | 16/06/2025 | SUDIP PRADHAN | 11.3 | 0 | 0 | 0
Total | [13 empty] | 5891.69 | 0 | 0