## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | GHOL DIGRUI (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000070/2023-2024 | 1273/HUG | 04/05/2023 | 29/03/2025 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 549.14 | 506.36 | 92.21 | 60
2 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/000186/2022-2023 | 779/ED | 09/02/2023 | 10/05/2023 | TRIO CONCERN | 22.03 | 22 | 99.88 | 75
3 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Material Requisition To Resource Division |  |  | RTOR000467/2023-2024 | 3057/17/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 15.63 | 0 | 0 | 0
4 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Material Requisition To Resource Division |  |  | RTOR000229/2022-2023 | 127/09/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 22.34 | 0 | 0 | 0
5 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1263/4/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 13.62 | 0 | 0 | 0
6 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Quotation Bill for New Service Connection at Gholdhuguri W/S. Sch. |  |  | BILL/02139/2023-2024 | 123 | 20/07/2023 | 20/07/2023 | WBSEDCL | 3.77 | 0 | 0 | 0
7 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Zone-I PH-I |  |  | BILL/02733/2023-2024 | 171 | 10/08/2023 | 10/08/2023 | WBSEDCL | 5.99 | 0 | 0 | 0
8 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GHOLDIGRUI (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000810/2023-2024 | 591/HUG | 22/02/2024 | 01/08/2026 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 31.57 | 13.75 | 43.57 | 70
9 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GHOLDIGRUI (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000885/2023-2024 | 809/HUG | 11/03/2024 | 01/08/2026 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 31.59 | 13.44 | 42.53 | 70
10 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for GHOLDIGRUI ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000291/2024-2025 | 3670/HUG | 13/11/2024 | 01/08/2026 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 26.4 | 0 | 0 | 30
11 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1,Junior Engineer3 | ORD/002467/2023-2024 | 328/ED | 21/02/2024 | 01/06/2026 | DEY ENTERPRISE | 10.43 | 0 | 0 | 5
12 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PURBATHAKURANICHAK PWSS -3 no¿s (2) DHARAMPUR PWSS- 3 no¿s (3) MAHISGHOT PWSS(Z-I)- 3no¿s (4) MAINAN PWSS- 2 no¿s (5) GHOLDIGRUI PWSS(Z-I)- 3no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/002305/2024-2025 | 1155/Arg | 10/12/2024 | 08/06/2025 | M/S KHAMRUI CONSTRUCTION | 0.98 | 0 | 0 | 99
13 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Quotation money deposition for new service connection at Gholedigrui w/s scheme, Zone- I, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004475357 Reference ID- 503799179 SM Code- 13334 |  |  | BILL/02304/2024-2025 | BP-24-25-596 | 21/11/2024 | 21/11/2024 | WBSEDCL | 6.98 | 0 | 0 | 0
14 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Electric quot. of WBSEDCL for New service Connection of Gholdigrui Zone-I T/W-III W/S scheme under Electrical Division PHE Dte. (SM/13334) |  |  | BILL/01265/2024-2025 | C032555994400 | 18/03/2025 | 18/03/2025 | WBSEDCL | 21.46 | 0 | 0 | 0
15 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Security Deposit for Gholdiguri water supply scheme, Zone-I,TW NO-IV (NEAR JASAR HEALTH CENTER) |  |  | BILL/01016/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 3.96 | 0 | 0 | 0
Total | [13 empty] | 765.9 | 555.55 | 72.54