## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Material Requisition To Resource Division |  |  | RTOR000467/2023-2024 | 3057/17/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 15.63 | 0 | 0 | 0
2 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Material Requisition To Resource Division |  |  | RTOR000229/2022-2023 | 127/09/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 22.34 | 0 | 0 | 0
3 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1263/4/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 13.62 | 0 | 0 | 0
4 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Quotation Bill for New Service Connection at Gholdhuguri W/S. Sch. |  |  | BILL/02139/2023-2024 | 123 | 20/07/2023 | 20/07/2023 | WBSEDCL | 3.77 | 0 | 0 | 0
5 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Zone-I PH-I |  |  | BILL/02733/2023-2024 | 171 | 10/08/2023 | 10/08/2023 | WBSEDCL | 5.99 | 0 | 0 | 0
6 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1,Junior Engineer3 | ORD/002467/2023-2024 | 328/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
7 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/000186/2022-2023 | 779/ED | 09/02/2023 | 10/05/2023 | TRIO CONCERN | 22.03 | 0 | 0 | 75
8 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Quotation money deposition for new service connection at Gholedigrui w/s scheme, Zone- I, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004475357 Reference ID- 503799179 SM Code- 13334 |  |  | BILL/02304/2024-2025 | BP-24-25-596 | 21/11/2024 | 21/11/2024 | WBSEDCL | 6.98 | 0 | 0 | 0
9 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GHOLDIGRUI (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000810/2023-2024 | 591/HUG | 22/02/2024 | 01/01/2026 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 31.57 | 0 | 0 | 70
10 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GHOLDIGRUI (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000885/2023-2024 | 809/HUG | 11/03/2024 | 01/01/2026 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 31.59 | 0 | 0 | 70
11 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for GHOLDIGRUI ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000291/2024-2025 | 3670/HUG | 13/11/2024 | 01/01/2026 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 26.4 | 0 | 0 | 30
12 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13334 | New | GHOL DIGRUI (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000070/2023-2024 | 1273/HUG | 04/05/2023 | 29/03/2025 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 549.14 | 0 | 0 | 60
Total | [13 empty] | 739.5 | 0 | 0