## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME | SM/13335 | New | Material Requisition To Resource Division |  |  | RTOR000196/2022-2023 | 109/ 11/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 11.55 | 0 | 0 | 0
2 | HOOGHLY | Haripal | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME | SM/13335 | New | Material Requisition To Resource Division |  |  | RTOR000277/2022-2023 | 902/10/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 14.48 | 0 | 0 | 0
3 | HOOGHLY | Haripal | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME | SM/13335 | New | Material Requisition To Resource Division |  |  | RTOR000209/2023-2024 | 1383/12/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 14.48 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME | SM/13335 | New | Material Requisition To Resource Division |  |  | RTOR000386/2023-2024 | 3058/28/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.48 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Electrical | PARJANA PIPED WATER SUPPLY SCHEME | SM/13335 | New | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Parjana water supply scheme, T.W. No.- I, II & III, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000178/2022-2023 | 771/ED | 09/02/2023 | 10/05/2023 | WEST BENGAL ENGINEERING CO. | 32.05 | 0 | 0 | 30
6 | HOOGHLY | Haripal | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME | SM/13335 | New | PARJANA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000102/2023-2024 | 1406/Hug | 17/05/2023 | 11/02/2024 | S & P ENTERPRISE | 659.08 | 0 | 0 | 50
7 | HOOGHLY | Haripal | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME | SM/13335 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Barakamalpur (Z-4) 1st T/W site & Parjana 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000282/2024-2025 | 921/Chan | 05/11/2024 | 20/11/2024 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
8 | HOOGHLY | Haripal | Electrical | PARJANA PIPED WATER SUPPLY SCHEME | SM/13335 | New | Quotation Bill for New Service Connection at Parjana W/S. Sch. TW-II |  |  | BILL/05965/2023-2024 | 722 | 31/01/2024 | 31/01/2024 | WBSEDCL | 7.3 | 0 | 0 | 0
9 | HOOGHLY | Haripal | Electrical | PARJANA PIPED WATER SUPPLY SCHEME | SM/13335 | New | Quotation Bill for New Service Connection at Parjana W/S. Sch. TW-I |  |  | BILL/05964/2023-2024 | 721 | 31/01/2024 | 31/01/2024 | WBSEDCL | 8.41 | 0 | 0 | 0
Total | [13 empty] | 762.78 | 0 | 0