## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Electrical | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bade Digaria water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000170/2022-2023 | 559/ED | 02/02/2023 | 03/05/2023 | M/S A.K BANERJEE | 21.37 | 0 | 0 | 0
2 | HOOGHLY | Haripal | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Material Requisition To Resource Division |  |  | RTOR000197/2022-2023 | 109/ 12/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 3.49 | 0 | 0 | 0
3 | HOOGHLY | Haripal | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Material Requisition To Resource Division |  |  | RTOR000276/2022-2023 | 902/12/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 10.26 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Material Requisition To Resource Division |  |  | RTOR000217/2023-2024 | 1383/19/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 10.26 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Material Requisition To Resource Division |  |  | RTOR000459/2023-2024 | 3058/27/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 10.26 | 0 | 0 | 0
6 | HOOGHLY | Haripal | Electrical | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Quotation for new Service Connection of Bade Digaria w/s Scheme, TW No-II, Block- Haripal, District- Hooghly under ED ,PHE DTE |  |  | BILL/01983/2023-2024 | 99 | 17/07/2023 | 17/07/2023 | WBSEDCL | 2.3 | 0 | 0 | 0
7 | HOOGHLY | Haripal | Electrical | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Quotation for New Service Connection of Bade Digaria W/S scheme,TW No-I, Block-Haripal, District- Hooghly under ED ,PHE Dte |  |  | BILL/01982/2023-2024 | 98 | 17/07/2023 | 17/07/2023 | WBSEDCL | 3.05 | 0 | 0 | 0
8 | HOOGHLY | Haripal | Electrical | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bade Digaria water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000171/2022-2023 | 764/ED | 09/02/2023 | 10/05/2023 | M/S A.K BANERJEE | 21.37 | 0 | 0 | 40
9 | HOOGHLY | Haripal | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Horizontal Auger boring with water jet system Including Culvert, Approach Road at BADE DIGHARIA Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000527/2023-2024 | 3006/HUG | 05/10/2023 | 04/12/2023 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 11.3 | 0 | 0 | 100
10 | HOOGHLY | Haripal | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Route Survey, Design Drawing & DPR preparation of Bade Digharia PWSS under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000634/2023-2024 | 521/Chan | 12/10/2023 | 27/10/2023 | APEX ENGINEERING | 4.19 | 0 | 0 | 100
11 | HOOGHLY | Haripal | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Bade Digaria PWSS, Bhagabatipur PWSS, Sirazpur PWSS, Harat PWSS, panrra PWSS, Malia PWSS) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000978/2023-2024 | 306/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0 | 0 | 100
12 | HOOGHLY | Haripal | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME | SM/13336 | New | BADE DIGARIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls at different TW site under HARIPAL Block, District- Hooghly.[NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000019/2023-2024 | 1062/HUG | 12/04/2023 | 01/07/2025 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 423.74 | 0 | 0 | 25
Total | [13 empty] | 522.54 | 0 | 0