## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Material Requisition To Resource Division |  |  | RTOR000492/2023-2024 | 3059/18/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 16.31 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 1264/22/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 21.65 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000325/2023-2024 | 2408/HUG | 11/08/2023 | 25/09/2023 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 24.08 | 29.5 | 20
4 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | ROAD RESTORATION PAYMENT TO PWD FOR BHANDARHATI KUMRUL ROAD |  |  | BILL/00662/2024-2025 | BP-2024-25-499 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 5.52 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2023-2024 | 2066/HUG | 17/07/2023 | 02/08/2025 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 172.02 | 7.63 | 20
6 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Shrirampur Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000334/2023-2024 | 2418/HUG | 11/08/2023 | 22/03/2025 | GEE BEE NIRMAN CO PRIVATE LIMITED | 52.91 | 8.57 | 16.2 | 25
7 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Dhaniakhali Block (Part-IV) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/002234/2024-2025 | 408/CH | 10/03/2025 | 25/03/2025 | TECHVISION | 4.2 | 0 | 0 | 0
8 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Construction of Store room for temporary Chlorine and maintenance material storage For Dasghara Zone-II, Gurbari and Shrirampur Piped Water Supply under Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001035/2023-2024 | 278/CH | 14/03/2024 | 21/03/2024 | SRI KRISHNA ENTERPRISE | 0.95 | 0 | 0 | 50
Total | [13 empty] | 2439.05 | 204.67 | 8.39