## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Electrical | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01120/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 104.27 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Electrical | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shrirampur water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000089/2023-2024 | 2068/ED | 30/05/2023 | 28/08/2023 | PURUSHOTTAM ENTERPRISE | 20.35 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Shrirampur Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000334/2023-2024 | 2418/HUG | 11/08/2023 | 09/11/2023 | GEE BEE NIRMAN CO PRIVATE LIMITED | 52.91 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Material Requisition To Resource Division |  |  | RTOR000492/2023-2024 | 3059/18/Hug | 11/10/2023 |  | Resource Division | 16.31 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Construction of Store room for temporary Chlorine and maintenance material storage For Dasghara Zone-II, Gurbari and Shrirampur Piped Water Supply under Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/001035/2023-2024 | 278/CH | 14/03/2024 | 21/03/2024 | SRI KRISHNA ENTERPRISE | 0.95 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2023-2024 | 2066/HUG | 17/07/2023 | 12/05/2024 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 34.09 | 1.51 | 20
7 | HOOGHLY | Dhaniakhali | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/13337 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000325/2023-2024 | 2408/HUG | 11/08/2023 | 25/09/2023 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 0 | 0 | 20
Total | [13 empty] | 2532.3 | 34.09 | 1.35