## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Quotation for new service connection at Dubir Bheri W/S Sch.(Aug.) , T/W no. - I, Dt. - Hooghly |  |  | BILL/02846/2023-2024 | 193 | 17/08/2023 | 17/08/2023 | WBSEDCL | 10.34 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Quotation for new service connection at Dubir Bheri W/S Sch(Aug.)., T/W No. - II, Hooghly |  |  | BILL/02847/2023-2024 | 194 | 17/08/2023 | 17/08/2023 | WBSEDCL | 8.98 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Preparation of DPR for Augmentation DUBIR BHERI Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil) |  | ORD/000078/2024-2025 | 693/CH | 09/08/2024 | 16/08/2024 | APEX ENGINEERING | 4.5 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Dubir Bheri PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000802/2023-2024 | 145/CH | 20/02/2024 | 27/02/2024 | R.K. TRADERS | 0.95 | 0 | 0 | 50
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Source Augmentation of DUBIRBHERI Piped Water Supply Scheme by Sinking 2 Nos. Tube well , Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Repairing of Switch Room & Boundary Wall and other allied work to meet up the water demand, due to execution of FHTC under Hooghly Division P.H.E. Dte. within Polba Dadpur Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000687/2022-2023 | 282/HUG | 01/02/2023 | 02/02/2025 | BIMAL KUMAR HALDER | 150.96 | 0 | 0 | 95
6 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dubir Bheri water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000207/2022-2023 | 834/ED | 14/02/2023 | 09/05/2024 | BARISAL TRADING CO. | 21.49 | 0 | 0 | 90
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Badinan PWSS 2. Hanral PWSS 3. Rajhat PWSS 4. Dibur Bheri PWSS 5. Akna PWSS 6. Harit PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000823/2023-2024 | 201/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 50
Total | [13 empty] | 198.18 | 0 | 0