## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Quotation for new service connection at Dubir Bheri W/S Sch.(Aug.) , T/W no. - I, Dt. - Hooghly |  |  | BILL/02846/2023-2024 | 193 | 17/08/2023 | 17/08/2023 | WBSEDCL | 10.34 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Quotation for new service connection at Dubir Bheri W/S Sch(Aug.)., T/W No. - II, Hooghly |  |  | BILL/02847/2023-2024 | 194 | 17/08/2023 | 17/08/2023 | WBSEDCL | 8.98 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Preparation of DPR for Augmentation DUBIR BHERI Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil) |  | ORD/000078/2024-2025 | 693/CH | 09/08/2024 | 16/08/2024 | APEX ENGINEERING | 4.5 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Dubir Bheri PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000802/2023-2024 | 145/CH | 20/02/2024 | 27/02/2024 | R.K. TRADERS | 0.95 | 0 | 0 | 50
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Source Augmentation of DUBIRBHERI Piped Water Supply Scheme by Sinking 2 Nos. Tube well , Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Repairing of Switch Room & Boundary Wall and other allied work to meet up the water demand, due to execution of FHTC under Hooghly Division P.H.E. Dte. within Polba Dadpur Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000687/2022-2023 | 282/HUG | 01/02/2023 | 02/02/2025 | BIMAL KUMAR HALDER | 150.96 | 0 | 0 | 95
6 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13343 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dubir Bheri water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000207/2022-2023 | 834/ED | 14/02/2023 | 09/05/2024 | BARISAL TRADING CO. | 21.49 | 0 | 0 | 90
Total | [13 empty] | 197.22 | 0 | 0