## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13344 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000364/2023-2024 | 3004/15/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 37.77 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13344 | Augmentation | Quotation Bill for New Service Connection at Bainchi W/S. Sch. PH-IV |  |  | BILL/04499/2023-2024 | 545 | 19/12/2023 | 19/12/2023 | WBSEDCL | 3.53 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13344 | Augmentation | Quotation Bill for New Service Connection at Bainchi W/S. Sch. PH-V |  |  | BILL/04498/2023-2024 | 544 | 19/12/2023 | 19/12/2023 | WBSEDCL | 36.89 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13344 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baichi water supply scheme, T.W. No.- I & II, Block: Pandua, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer6 | ORD/000196/2022-2023 | 823/ED | 14/02/2023 | 15/05/2023 | SRI KRISHNA NIRMAN | 21.49 | 20.94 | 97.45 | 90
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13344 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in BATIKA-BAINCHI GP of PANDUA Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000922/2023-2024 | 242/CH | 12/03/2024 | 11/04/2024 | RAJMAHAL ENTERPRISE | 4.99 | 4.81 | 96.55 | 90
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13344 | Augmentation | Sinking of 02Nos. Tube well with, Laying Distribution System, Laying rising main pipe for inter connection between T.W & Distribution pipeline, Construction of Switch Rooms & Boundary Wall in Proposed T.W Sites, Repairing of Switch Rooms & Boundary Wall and other allied works for Bainchi Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.HE Dte. of Panuda Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000543/2023-2024 | 3109/HUG | 13/10/2023 | 05/03/2025 | BAPPADITYA BANERJEE | 144.46 | 67.69 | 46.85 | 24
Total | [13 empty] | 249.13 | 93.44 | 37.51