## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Quotation bill for New Service Connection Kulihanda W/S. Sch. pH-II |  |  | BILL/00855/2022-2023 | 175 | 28/02/2023 |  | WBSEDCL | 4.33 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda W/S. Sch. TW-IV, Hooghly |  |  | ORD/001136/2022-2023 | 1037/ED | 28/06/2022 | 26/09/2022 | STANDARD ELECTRICALS | 10.23 | 10.21 | 99.76 | 0
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Quotation Bill for New Service Connection at Kulihanda W/S. Sch. TW-VI |  |  | BILL/04243/2023-2024 | 420 | 10/11/2023 |  | WBSEDCL | 5.1 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Hiring of Luxury Car/Ambassador (BS-IV) for official use of the Chief Engineer (Electrical/Mechanical) Southern Zone, PHE Dte. |  |  | ORD/001170/2023-2024 | 1072/HMSD | 11/05/2023 | 10/05/2024 | ORIENTAL ENGINEERING CO. | 0.95 | 0.26 | 27.15 | 80
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000162/2022-2023 | 3497/ED | 30/12/2022 | 30/03/2023 | H.K.DAS & CO. | 10.82 | 10.66 | 98.51 | 100
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Repairing of Switch Room & Boundary Wall and other allied work for Source Augmentation of KULIHANDA Piped Water Supply Scheme Under Hooghly Division P.H.E. Dte. within Chinsurah Mogra Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000691/2022-2023 | 327/HUG | 03/02/2023 | 04/05/2023 | PREMANANDA ROY BISWAS | 121.55 | 71.19 | 58.57 | 80
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under CHINSURAH-MOGRA Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000342/2023-2024 | 2427/HUG | 11/08/2023 | 10/09/2023 | SWASTIK ENTERPRISE | 42.74 | 26.58 | 62.19 | 95
8 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda water supply scheme, T.W. No. VI, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000855/2023-2024 | 3529/ED | 18/08/2023 | 16/11/2023 | N.S. TRADING | 10.56 | 10.27 | 97.28 | 90
9 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Quotation for new service connection at Kulihanda[SM/13345] W/S Sch., T/W No. - VII, Sukantanagar, Dt. - Hooghly, Ref. Id. - 503611685, Dt. - 8/04/2024, Application No. - 5004102924 under Pipulpati CCC, WBSEDCL |  |  | BILL/00137/2024-2025 | 55 | 12/04/2024 |  | WBSEDCL | 8.56 | 0 | 0 | null
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Sinking of 2 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) At KULIHANDA & SRIPUR W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill),Pandua Block Junior Engineer (Civill) | ORD/000326/2023-2024 | 2409/HUG | 11/08/2023 | 10/09/2023 | OSMAN SEKH | 32.34 | 0 | 0 | 100
11 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13345 | Augmentation | Quotation for new service connection at Kulihanda W/S (Aug.)[SM/13345] Scheme, T/W No. - VIII,(Adarsha Nagar, Panditjir Dokan) under Bandel CCC, WBSEDCL, Ref. Id. - 503647843, Dt. - 17-05-2024, Application No. - 5004191804 |  |  | BILL/00514/2024-2025 | 177 | 30/05/2024 |  | WBSEDCL | 6.18 | 0 | 0 | null
Total | [13 empty] | 253.36 | 129.17 | 50.98