## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13346 | Augmentation | Withdrawing Existing C.I Pipes & Specials & Laying CI/DI Pipes & Specials for Rising main pipeline for AMODGHATA W/S under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000251/2022-2023 | 717 CH | 23/08/2022 | 07/09/2022 | SHREEOM ENTERPRISE | 1.77 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13346 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Amodghata water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000278/2022-2023 | 945/ED | 22/02/2023 | 23/05/2023 | JOYSHREE CONCERN | 10.83 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13346 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 4th T/W Site of AMODGHATA W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000254/2022-2023 | 721/CH | 23/08/2022 | 07/10/2022 | S B ENTERPRISE | 4.97 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13346 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Amodghata water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000236/2022-2023 | 867/ED | 14/02/2023 | 15/05/2023 | JOYSHREE CONCERN | 10.83 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13346 | Augmentation | Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Repairing of Switch Room & Boundary Wall and other allied work for Source Augmentation of AMODGHATA Piped Water Supply Scheme Under Hooghly Division P.H.E Dte within Chinsurah Mogra Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000688/2022-2023 | 283/HUG | 01/02/2023 | 02/05/2023 | R.K. TRADERS | 115.44 | 0 | 0 | 75
6 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13346 | Augmentation | Quotation bill for new service connection at Amodghata w/s scheme |  |  | BILL/00840/2022-2023 | 174 | 28/02/2023 | 28/02/2023 | WBSEDCL | 7.19 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13346 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Amodghata PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000803/2023-2024 | 146/CH | 20/02/2024 | 27/02/2024 | R.K. TRADERS | 0.95 | 0 | 0 | 50
8 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13346 | Augmentation | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. with allied works for Amodghata W/S. Sch. TW- IV, Hooghly | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000870/2022-2023 | 1547/ED | 20/09/2022 | 19/12/2022 | BISALAXMI ENTERPRISE | 9.64 | 0 | 0 | 99
Total | [13 empty] | 161.63 | 0 | 0