## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-II | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Rectification & overhualing of VCB Panel, LT Panel, ATS Panel, AVR and transformer at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001207/2021-2022 | 145/AE-I/ED | 18/02/2022 | 19/05/2022 | ORIENTAL ENGINEERING CO. | 1.9 | 0 | 0 | 0
2 | HOOGHLY | Chanditala-II | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Supply & Installation of NRV and other allied works at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001208/2021-2022 | 1009/AE-I/ED | 13/08/2021 | 11/11/2021 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0 | 0
3 | HOOGHLY | Chanditala-II | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Supply & Installation of Butterfly valve for pump set no-2 at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001210/2021-2022 | 42/AE-I/ED | 14/01/2022 | 14/04/2022 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0 | 0
4 | HOOGHLY | Chanditala-II | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Supply & Installation of Butterfly valve & Check valve for pump set no-3 at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001211/2021-2022 | 43/AE-I/ED | 14/01/2022 | 14/04/2022 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-II | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Material Requisition To Resource Division |  |  | RTOR000317/2023-2024 | 1384/14/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 11.08 | 0 | 0 | 0
6 | HOOGHLY | Chanditala-II | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Material Requisition To Resource Division |  |  | RTOR000494/2023-2024 | 3060/12/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 11.08 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-II | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Material Requisition To Resource Division |  |  | RTOR000167/2022-2023 | 79/10/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 11.08 | 0 | 0 | 0
8 | HOOGHLY | Chanditala-II | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Madhavpur w/s scheme,P H No 1 |  |  | BILL/03774/2023-2024 | 273 | 08/09/2023 | 08/09/2023 | WBSEDCL | 3.71 | 0 | 0 | 0
9 | HOOGHLY | Chanditala-II | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Madhavpur w/s scheme,P H No 2 |  |  | BILL/04511/2023-2024 | 554 | 21/12/2023 | 21/12/2023 | WBSEDCL | 6.73 | 0 | 0 | 0
10 | HOOGHLY | Chanditala-II | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Madhabpur Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-II Block, District:- Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000690/2022-2023 | 326/HUG | 03/02/2023 | 01/04/2025 | ARUN SEAL AND CO. | 443.64 | 0 | 0 | 50
11 | HOOGHLY | Chanditala-II | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | CONSTRUCTION OF 2Nos. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT MADHABPUR HW SITE AND KUMIRMORA Z-I 2ND TW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000147/2024-2025 | 430/SER | 31/07/2024 | 15/08/2024 | SUNITI MAIRA | 0.68 | 0 | 0 | 95
12 | HOOGHLY | Chanditala-II | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | SM/13347 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Madhabpur water supply scheme TW No I and II Block Chanditala II District Hooghly under ED PHED. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000231/2022-2023 | 862/ED | 14/02/2023 | 01/08/2025 | NEW RANBEE ENGINEERING | 20.36 | 0 | 0 | 40
Total | [13 empty] | 523.92 | 0 | 0