## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Repairing of 3.6 mtr. x 3.0 mtr. size existing pump house of Purba Ramnagar PWSS scheme under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000575/2021-2022 | 660/CHAN | 27/12/2021 | 26/01/2022 | SWASTIK ENTERPRISE | 2.75 | 2.58 | 93.66 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Repairing of 5.4 mtr x 3.6 mtr size existing pump house of Purba Ramnagar PWSS scheme under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000574/2021-2022 | 534/CHAN | 12/11/2021 | 12/12/2021 | SWASTIK ENTERPRISE | 2.96 | 2.94 | 99.26 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2022-2023 | 2686/4/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.32 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Route survey Design drawing & DPR preparation of Purba Ramnagar PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) |  | ORD/000178/2022-2023 | 272/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.03 | 95.01 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000298/2023-2024 | 1383/42/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 27.81 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 1235/14/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 71.65 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000464/2023-2024 | 3058/26/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 28 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Purba Ramnagar w/s scheme,P H No 3 |  |  | BILL/03772/2023-2024 | 275 | 08/09/2023 | 08/09/2023 | WBSEDCL | 4.62 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. |  |  | BILL/00229/2022-2023 | BP-2022-23-546 | 21/02/2023 | 21/02/2023 | GOUR KUMAR DAS | 0.65 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Purba Ramnagar w/s scheme,P H NO 4 |  |  | BILL/03773/2023-2024 | 274 | 08/09/2023 | 08/09/2023 | WBSEDCL | 5.06 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | Purba Ramnagar w/s scheme,P H No . 3 |  |  | BILL/03771/2023-2024 |  | 05/09/2023 | 05/09/2023 | WBSEDCL | 4.62 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | SM/13348 | Augmentation | AUGMENTATION of PURBA RAMNAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Repairing of Existing Switch Rooms, Boundary Wall of existing T.W Sites, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under TARAKESWAR Block, District:- Hooghly [AUGMENTATION SCHEME] [2nd Call of WBPHE/EE/33/HUG/2022-23(Sl No. 4)] | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | ORD/000229/2023-2024 | 2062/HUG | 17/07/2023 | 16/10/2025 | BANSBERIA CONSTRUCTION CO. | 789.94 | 708.35 | 89.67 | 55
Total | [13 empty] | 942.62 | 717.89 | 76.16