## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2022-2023 | 2686/11/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.35 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Route survey Design drawing & DPR preparation of Sripatipur PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000168/2022-2023 | 263/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.83 | 4.8 | 99.46 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000277/2023-2024 | 1383/27/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 20.33 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000207/2022-2023 | 109/7/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 20.06 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Quotation of New Service Connection for Sripatipur w/s scheme,Zone-II,TW No-II Block-Haripal Dist-Hooghly under ED,PHE Dte |  |  | BILL/03765/2023-2024 | 260 | 05/09/2023 | 05/09/2023 | WBSEDCL | 6.19 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Quotation of New Service Connection for Sripatipur w/s Scheme,Z-I,TW No-3 Block-Haripal,District-Hooghly under Electrical Division PHE Dte |  |  | BILL/03886/2023-2024 | 299 | 22/09/2023 | 22/09/2023 | WBSEDCL | 2.5 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Quotation of New Service Connection for Sripatipur W/S Scheme,Zone-I,TW No-I Block-Haripal,Dist-Hooghly under ED,PHE Dte |  |  | BILL/03763/2023-2024 | 262 | 05/09/2023 | 05/09/2023 | WBSEDCL | 3.31 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Quotation for new service connection charge at Sripatipur PWSS, Zone-II, TW - II |  |  | BILL/04486/2023-2024 | 531 | 15/12/2023 | 15/12/2023 | WBSEDCL | 3.22 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, PHE DTE. |  |  | BILL/00345/2023-2024 | BP-2023-24-281 | 16/08/2023 | 16/08/2023 | GOUR KUMAR DAS | 0.77 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Quotation of New Service Connection for sripatipur W/S Scheme,Zone-I,TW No-II Block-Haripal Dist-Hooghly under ED,PHE Dte |  |  | BILL/03764/2023-2024 | 261 | 05/09/2023 | 05/09/2023 | WBSEDCL | 3.16 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | AUGMENTATION of SRIPATIPUR ZONE-II Piped Water Supply Scheme with Construction of switch room, LDS, Boundary Wall, LDS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. Block-SINGUR, District- Hooghly.[AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000018/2023-2024 | 1063/HUG | 12/04/2023 | 11/07/2023 | SATYA NARAYAN BISWAS | 215.71 | 171.28 | 79.41 | 50
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | AUGMENTATION of SRIPATIPUR ZONE-I Piped Water Supply Scheme with Construction of Switch Room, Boundary Wall, LDS, under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. Block-SINGUR, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000802/2022-2023 | 953/HUG | 30/03/2023 | 28/06/2023 | MALLIKA ENTERPRISE | 156.56 | 144.41 | 92.24 | 100
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of SRIPATIPUR W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000204/2023-2024 | 1819/HUG | 22/06/2023 | 06/08/2023 | OSMAN SEKH | 80.85 | 80.54 | 99.63 | 45
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of boundary wall at Proposed H.W site, Rising Main, FHTC For AUGMENTATION of SRIPATIPUR ZONE-I Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000120/2023-2024 | 1470/HUG | 19/05/2023 | 01/01/2026 | SOUMYADIP DE | 181.5 | 82.92 | 45.69 | 70
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Providing FHTC for the leftout portion of Sripatipur Mouza of SRIPATIPUR ZONE 1 Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000358/2024-2025 | 3666/HUG | 13/11/2024 | 01/10/2025 | TRIYA CONSTRUCTION | 36.22 | 0 | 0 | 100
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Construction of approach road at head work site of Sripatipur zone-I water supply scheme under Chandannagar Sub-Division P.H.E. Dte.(Part-B) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002213/2024-2025 | 195/Chan | 12/02/2025 | 04/03/2025 | SOUMYADIP DE | 3.95 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | :Estimate for Supply fitting and fixing of sluice valve for Sripatipur Zone-II Water Supply Scheme Under Chandannagar SubDivision,P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000257/2025-2026 | 905/CHAN | 21/07/2025 | 05/08/2025 | MAA TARA CONSTRUCTION | 4.92 | 0 | 0 | 50
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Repairing of boundary wall at old 1st tubewell site of Sripatipur z-2 PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000286/2025-2026 | 919/CHAN | 21/07/2025 | 10/08/2025 | M/S T.K.B. CONSTRUCTION | 4.18 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Repairing of boundary wall at old 2nd site of Sripatipur z-2 PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000287/2025-2026 | 920/CHAN | 21/07/2025 | 10/08/2025 | M/S T.K.B. CONSTRUCTION | 2.09 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Sripatipur water supply scheme TW No I II III IV and V, Block Haripal, District Hooghly under ED PHED. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000230/2022-2023 | 861/ED | 14/02/2023 | 17/07/2025 | DEY ENTERPRISE | 53.74 | 52.19 | 97.11 | 65
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Providing FHTC for the leftout portion of SRIPATIPUR ZONE 1 Water Supply Scheme | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000881/2023-2024 | 773/HUG | 06/03/2024 | 01/05/2025 | SOUMYADIP DE | 7.93 | 5.22 | 65.84 | 80
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Approach road at Sripatipur H/W site under Sripatipur Zone1 water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. (Part- A) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002216/2024-2025 | 197/Chan | 12/02/2025 | 04/03/2025 | SOUMYADIP DE | 4.9 | 0 | 0 | 100
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | SM/13349 | Augmentation | Road restoration at Sripatipur zone-I water supply scheme under Chandannagar Sub-Division P.H.E. Dte.(Part-B) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002215/2024-2025 | 196/Chan | 12/02/2025 | 04/03/2025 | SOUMYADIP DE | 4.97 | 0 | 0 | 100
Total | [13 empty] | 822.24 | 541.38 | 65.84