## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Ketera Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR underChandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000586/2022-2023 | 2845/HUG | 16/12/2022 | 15/01/2023 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 22.7 | 12.58 | 55.43 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Gayeshpur & Bishnubati Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR underChandannagar Sub-Division of Hooghly Division P.H.E Dte.1 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000587/2022-2023 | 2846/HUG | 16/12/2022 | 15/01/2023 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 31.27 | 30.56 | 97.72 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Ramnarayanpur Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000778/2022-2023 | 790/HUG | 20/03/2023 | 19/04/2023 | AHS R INFRA PRIVATE LIMITED | 25.02 | 21.17 | 84.6 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Samanta Para of Ramnarayanpur PWSS under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000380/2023-2024 | 389/Chan | 09/06/2023 | 24/06/2023 | KALYAN BANERJEE | 0.93 | 0.92 | 99.9 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Gure & Makrar Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR underChandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000588/2022-2023 | 2847/HUG | 16/12/2022 | 15/01/2023 | ARATI ENGINEERING | 34.16 | 34.12 | 99.89 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13353 | Retrofitting | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas of Ramnarayanpur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000856/2023-2024 | 728/HUG | 05/03/2024 | 19/04/2024 | SWASTIK ENTERPRISE | 33.9 | 17.91 | 52.83 | 80
Total | [13 empty] | 147.97 | 117.26 | 79.25