## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF GHOSHPUR PWSS FOR PROVIDING 4709 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13354 | Retrofitting | Supply of 200 mm dia CD pipe for Sinking of Tubewell at Ghoshpur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001049/2023-2024 | 470/Arg | 05/07/2023 | 20/07/2023 | MAYA CONSTRUCTION | 0.97 | 0.48 | 50 | 100
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF GHOSHPUR PWSS FOR PROVIDING 4709 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | SM/13354 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in GHOSHPUR PWSS, Block KHANAKUL-I under Arambag Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000245/2023-2024 | 2100/HUG | 19/07/2023 | 02/09/2023 | GHOSH BROTHERS | 95.26 | 0 | 0 | 80
Total | [13 empty] | 96.22 | 0.48 | 0.5