## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 1235/11/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 85.79 | 0 | 0 | 0
2 | HOOGHLY | Haripal | Hooghly Division | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | Material Requisition To Resource Division |  |  | RTOR000203/2023-2024 | 1383/6/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 22.24 | 0 | 0 | 0
3 | HOOGHLY | Haripal | Hooghly Division | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | Material Requisition To Resource Division |  |  | RTOR000415/2023-2024 | 3058/25/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.85 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | new service connection |  |  | BILL/02600/2023-2024 | 164 | 03/08/2023 | 03/08/2023 | WBSEDCL | 1.7 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | new service connection |  |  | BILL/02602/2023-2024 | 165 | 03/08/2023 | 03/08/2023 | WBSEDCL | 3.25 | 0 | 0 | 0
6 | HOOGHLY | Haripal | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bahirkhanda water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000126/2022-2023 | 3481/ED | 30/12/2022 | 28/02/2023 | S.M. ELECTRICALS | 21.48 | 0 | 0 | 60
7 | HOOGHLY | Haripal | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bahir Khanda water supply scheme, T.W. No. III, Block: Tarakeswar, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2,Junior Engineer4 | ORD/002482/2023-2024 | 342/ED | 21/02/2024 | 21/05/2024 | JOYSHREE CONCERN | 10.58 | 0 | 0 | 20
8 | HOOGHLY | Haripal | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | Quotation of New Service Connection for Bahir Khanda w/S Scheme,TW No-3 Block-Haripal Dist-Hooghly under ED,PHE Dte. (SM/13404) Application No-5003976156 Reference Id-503538913 |  |  | BILL/06473/2023-2024 | 900 | 19/03/2024 | 19/03/2024 | WBSEDCL | 3.58 | 0 | 0 | 0
9 | HOOGHLY | Haripal | Hooghly Division | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | BAHIRKHANDA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block of Chandannagar Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] [2nd Call of WBPHE/EE/51/HUG/2022-23(Sl No. 3)] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000171/2023-2024 | 1670/HUG | 08/06/2023 | 01/01/2026 | DIPTI TRADERS | 948.76 | 0 | 0 | 96
10 | HOOGHLY | Haripal | Hooghly Division | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | SM/13404 | New | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 5.4 m X 3.6 m Switch Roomwith Sanitary and Water Supply arrangement ,Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of BAHIRKHANDA Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000659/2023-2024 | 3524/HUG | 30/11/2023 | 02/03/2025 | DIPTI TRADERS | 32.12 | 0 | 0 | 100
Total | [13 empty] | 1144.34 | 0 | 0