## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Saptagram w/s scheme, P.H No.- IV, Dist- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000314/2022-2023 | 490/HMSD | 02/03/2023 | 01/04/2023 | M.S.C. ENTERPRISE | 2.49 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Saptagram water supply scheme, T.W. No. IV, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001248/2022-2023 | 1318/ED | 17/08/2022 | 15/11/2022 | M.S.C. ENTERPRISE | 7.28 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of SAPTAGRAM PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte.. | Assistant Engineer (Civil) |  | ORD/000031/2023-2024 | 1131/HUG | 19/04/2023 | 19/05/2023 | SWARNA ENTERPRISE | 24.19 | 0 | 0 | 98
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Construction of Boundary Wall, Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system, FHTC of SAPTAGRAM W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000086/2023-2024 | 1340/HUG | 11/05/2023 | 10/06/2023 | SWARNA ENTERPRISE | 21.02 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000351/2023-2024 | 3004/4/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 36.39 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Construction of 2nos. 3.6 mtr x3.0 mtr Switch Room with Additional Plinth Height, With Sanitary and Water Supply arrangement at Proposed T/W Sites for Saptagram Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at Chinsurah Mogra Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000853/2023-2024 | 736/HUG | 05/03/2024 | 19/04/2024 | M/S BIMAL DAS AND CO. | 11.17 | 0 | 0 | 50
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Sinking of 2 (Two) No Big dia tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at 3rd TW site of Saptagram W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000855/2023-2024 | 737/HUG | 05/03/2024 | 04/04/2024 | TAPAS ADHYA | 19.53 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Providing FHTC at the left out portions of Mithapukur for proiving FHTC in Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001038/2023-2024 | 280/CH | 14/03/2024 | 21/03/2024 | BIMAL KUMAR HALDER | 0.97 | 0 | 0 | 80
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Providing FHTC at the left out portions of Choto Khejuria for proiving FHTC in Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001040/2023-2024 | 282/CH | 14/03/2024 | 21/03/2024 | BIMAL KUMAR HALDER | 0.96 | 0 | 0 | 80
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Providing FHTC at the left out portions of Bara Khejuria for proiving FHTC in Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001041/2023-2024 | 283/CH | 14/03/2024 | 21/03/2024 | BIMAL KUMAR HALDER | 0.97 | 0 | 0 | 80
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Laying HDPE pipeline for proiving FHTC at different placess at Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001039/2023-2024 | 281/CH | 14/03/2024 | 21/03/2024 | BIMAL KUMAR HALDER | 0.96 | 0 | 0 | 80
12 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Quotation for new service connection at Saptagram (S.Aug.) W/S Sch. [SM/13409], T/W No. - II (Chotokhejuria),Block -Chinsurah- Mogra under Saptagram CCC, WBSDCL. Ref. Id - 503643407, dt. - 10-05-2024, Application No. - 5004179275 |  |  | BILL/00458/2024-2025 | 126 | 17/05/2024 | 17/05/2024 | WBSEDCL | 5.49 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Quotation for new service connection at Saptagram (S.Aug.) W/S Sch. [SM/13409], T/W No. - I (Dingalghat, bansberia),Block -Chinsurah- Mogra under Saptagram CCC, WBSDCL. Ref. Id - 503643287, dt. - 10-05-2024, Application No. - 5004179261 |  |  | BILL/00455/2024-2025 | 123 | 17/05/2024 | 17/05/2024 | WBSEDCL | 3.94 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAPTAGRAM PIPED W/S SCHEME, T.W. No. V & VI, Block: Chinsurah Mogra, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000352/2024-2025 | 1457/ED | 25/07/2024 | 23/10/2024 | D. K. ELECTRIC | 22.19 | 0 | 0 | 70
15 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at H/W Site of Saptagram Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000004/2025-2026 | 486/CH | 04/04/2025 | 14/04/2025 | BIMAL KUMAR HALDER | 4.53 | 0 | 0 | 100
16 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13409 | Augmentation | Repairing & Renovation of Switch room at PH-2 of Saptagram Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002010/2024-2025 | 296/CH | 20/02/2025 | 02/03/2025 | BIMAL KUMAR HALDER | 1.33 | 0 | 0 | 100
Total | [13 empty] | 163.43 | 0 | 0