## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of DIGSUI-HEORA ( Z-II) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000267/2022-2023 | 723/CH | 23/08/2022 | 07/10/2022 | SUDIPTA DAS | 4.98 | 0 | 0 | 100
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Digsui Heora W/S. Sch. |  |  | VCH/002738/2022-2023 |  | 10/11/2022 | 10/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 21.72 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | New Connection of Digsui Heora W/S. Sch. Z-I, PH-III |  |  | BILL/00002/2022-2023 | BP-2022-23-110 | 01/12/2022 | 01/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.91 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. with effect from 01.04.2023 to 31.08.2023. |  |  | ORD/001367/2022-2023 | 203/AE-I/ED | 27/03/2023 | 27/08/2023 | DASHRATH KUMAR PRAJAPATI | 0.73 | 0 | 0 | 5
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Digsui Heora water supply scheme, Zone-II, T.W. No.- III, Block: Chinsurah Mogra, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001366/2022-2023 | 1917/ED | 21/11/2022 | 19/02/2023 | M/S S.R. ENTERPRISE | 9.41 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of DIGSUI-HEORA ( Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000255/2022-2023 | 722/CH | 23/08/2022 | 07/10/2022 | SWARNA ENTERPRISE | 4.98 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Supply, delivery & installation of sautomatic chlorinatorfor Digsui Heora W/S. Sch. Z-I, TW-III Hooghly |  |  | ORD/002560/2022-2023 | 69/HMSD | 10/01/2023 | 17/01/2023 | SRI KRISHNA NIRMAN | 0.8 | 0 | 0 | 100
8 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Supply, Delivery & Installation of submersible pumping machinery & other Electrical Mechanical equipments etc. with allied works for Digsui- Heora W/S. Sch. TW-III |  |  | ORD/000241/2022-2023 | 1538/ED | 19/09/2022 | 18/12/2022 | SRI KRISHNA NIRMAN | 8.93 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000375/2023-2024 | 3004/6/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 37.77 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Quotation bill for New Connection of WBSEDCL at Digsui Heora W/S. Sch. |  |  | BILL/00774/2022-2023 | 127 | 17/01/2023 | 17/01/2023 | WBSEDCL | 3.83 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DIGSUI HEORAH PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte... | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000032/2023-2024 | 1132/HUG | 19/04/2023 | 19/05/2023 | RANA ENTERPRISE | 32.74 | 0 | 0 | 80
12 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Construction of Boundary Wall ,Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of DIGSUI HOERA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000085/2023-2024 | 1339/HUG | 11/05/2023 | 10/06/2023 | MAA JAGADHATRI CONSTRUCTION | 23.6 | 0 | 0 | 83
13 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Emergency Repairing & Replacing Different dia distribution pipeline and necessary allied Works At Digsui Hoera Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000730/2023-2024 | 19/CH | 04/01/2024 | 19/01/2024 | MAA BUNAMATA ENTERPRISE | 2.1 | 0 | 0 | 55
14 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Additional Laying of HDPE pipeline and interconnection work in distibution system of Digsui Heora Zone-I and Zone-II Water Supply Scheme for providing left over FHTC under Chinsurah Sub- Division, Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000790/2023-2024 | 535/HUG | 20/02/2024 | 06/03/2024 | MAA JAGADHATRI CONSTRUCTION | 16.41 | 0 | 0 | 25
15 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at H/W Site of Digsui Heora Z-II Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000007/2025-2026 | 489/CH | 04/04/2025 | 14/04/2025 | DAS ENTERPRISE (SAMIR DAS) | 4.51 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Digsui Heora Z-II Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/002012/2024-2025 | 300/CH | 20/02/2025 | 02/03/2025 | DAS ENTERPRISE (SAMIR DAS) | 2.06 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Shifting of distribution pipeline for widening of G.T. Roadfrom Naksa mouza to Hoera mouza of Digsui Hoera GP of Digsui Hoera Zone -I & Zone -II Water Supply Scheme under Chinsurah sub-division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001834/2024-2025 | 332/HUG | 05/02/2025 | 06/04/2025 | SAMRAT CONSTRUCTION | 27.36 | 0 | 0 | 25
Total | [13 empty] | 213.83 | 0 | 0