## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Digsui Heora W/S. Sch. |  |  | VCH/002738/2022-2023 | null | 10/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 21.72 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | New Connection of Digsui-Heora W/S. Sch. Z-II, PH-III |  |  | BILL/00001/2022-2023 | null | 22/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.81 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | New Connection of Digsui Heora W/S. Sch. Z-I, PH-III |  |  | BILL/00002/2022-2023 | BP-2022-23-110 | 01/12/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.91 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of DIGSUI-HEORA ( Z-II) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000267/2022-2023 | 723/CH | 23/08/2022 | 07/10/2022 | SUDIPTA DAS | 4.98 | 4.93 | 99.09 | 100
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Quotation bill for New Connection of WBSEDCL at Digsui Heora W/S. Sch. |  |  | BILL/00774/2022-2023 | 127 | 17/01/2023 |  | WBSEDCL | 3.83 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of DIGSUI-HEORA ( Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000255/2022-2023 | 722/CH | 23/08/2022 | 07/10/2022 | SWARNA ENTERPRISE | 4.98 | 4.97 | 99.97 | 0
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. with effect from 01.04.2023 to 31.08.2023. |  |  | ORD/001367/2022-2023 | 203/AE-I/ED | 27/03/2023 | 27/08/2023 | DASHRATH KUMAR PRAJAPATI | 0.73 | 0.39 | 53.97 | 5
8 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Supply, Delivery & Installation of submersible pumping machinery & other Electrical Mechanical equipments etc. with allied works for Digsui- Heora W/S. Sch. TW-III |  |  | ORD/000241/2022-2023 | 1538/ED | 19/09/2022 | 18/12/2022 | SRI KRISHNA NIRMAN | 8.93 | 8.88 | 99.51 | 100
9 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Digsui Heora water supply scheme, Zone-II, T.W. No.- III, Block: Chinsurah Mogra, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001366/2022-2023 | 1917/ED | 21/11/2022 | 19/02/2023 | M/S S.R. ENTERPRISE | 9.41 | 9.41 | 99.94 | 100
10 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Supply, delivery & installation of sautomatic chlorinatorfor Digsui Heora W/S. Sch. Z-I, TW-III Hooghly |  |  | ORD/002560/2022-2023 | 69/HMSD | 10/01/2023 | 17/01/2023 | SRI KRISHNA NIRMAN | 0.8 | 0.8 | 100 | 100
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Emergency Repairing & Replacing Different dia distribution pipeline and necessary allied Works At Digsui Hoera Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000730/2023-2024 | 19/CH | 04/01/2024 | 19/01/2024 | MAA BUNAMATA ENTERPRISE | 2.1 | 1.05 | 49.95 | 55
12 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DIGSUI HEORAH PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte... | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000032/2023-2024 | 1132/HUG | 19/04/2023 | 19/05/2023 | RANA ENTERPRISE | 32.74 | 21.91 | 66.93 | 80
13 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Construction of Boundary Wall ,Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of DIGSUI HOERA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000085/2023-2024 | 1339/HUG | 11/05/2023 | 10/06/2023 | MAA JAGADHATRI CONSTRUCTION | 23.6 | 3.7 | 15.67 | 83
14 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/13410 | Augmentation | Additional Laying of HDPE pipeline and interconnection work in distibution system of Digsui Heora Zone-I and Zone-II Water Supply Scheme for providing left over FHTC under Chinsurah Sub- Division, Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000790/2023-2024 | 535/HUG | 20/02/2024 | 06/03/2024 | MAA JAGADHATRI CONSTRUCTION | 16.41 | 0 | 0 | 25
Total | [13 empty] | 151.93 | 56.05 | 36.89