## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Quotation bill for Sripur W/S. Sch. |  |  | VCH/002751/2022-2023 | 108 | 18/11/2022 | 18/11/2022 | WBSEDCL | 2.96 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Quatation bill for Sripur W/S. Sch. PH-III |  |  | VCH/002739/2022-2023 |  | 10/11/2022 | 10/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.96 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of SRIPUR (PANDUA) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000270/2022-2023 | 725/CH | 23/08/2022 | 07/10/2022 | TOTON MONDAL | 4.99 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | "Supply, Delivery & Installation of S/P/M & other E/M equipments etc. for Sripur W/S. Sch. TW-III RA-I" | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/001034/2022-2023 | 1320/ED | 17/08/2022 | 15/11/2022 | SWAPAN ENTERPRISE | 7.37 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Withdrawing of 10 HP submersible pumping machinery and installation of standby pumping machinery and allied electrical/mechanical works at Sripur w/s scheme, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/001135/2022-2023 | 1991/HMSD | 10/11/2022 | 01/12/2022 | KUSHANI ENTERPRISE | 2.45 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000347/2023-2024 | 3004/2/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 37.77 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Supply Xerox Paper ofice of the EE PHE Dte |  |  | BILL/01915/2022-2023 | 253 | 31/03/2023 | 31/03/2023 | BARRACKPORE CENTRAL ZONE | 0.09 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under PANDUA Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000346/2023-2024 | 2429/HUG | 11/08/2023 | 10/09/2023 | GHOSH CONSTRUCTION | 42.89 | 0 | 0 | 80
9 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SRIPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pandua, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2,Junior Engineer6 | ORD/000170/2024-2025 | 1193/ED | 14/06/2024 | 12/09/2024 | SUBHRA ENTERPRISE | 10.75 | 0 | 0 | 60
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Construction of Boundary Wall ,Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of SRIPUR PANDUAH W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000084/2023-2024 | 1338/HUG | 11/05/2023 | 10/06/2023 | AMBIAN INFRASTRUTTURE | 16.02 | 0 | 0 | 85
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Sinking of 2 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) At KULIHANDA & SRIPUR W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill),Pandua Block Junior Engineer (Civill) | ORD/000326/2023-2024 | 2409/HUG | 11/08/2023 | 10/09/2023 | OSMAN SEKH | 32.34 | 0 | 0 | 100
12 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sripur village under Pandua Block, Panpara village of Pandua Block and Akna village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000989/2023-2024 | 263/CH | 14/03/2024 | 21/03/2024 | ASHA ENTERPRISE | 0.95 | 0 | 0 | 100
13 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Sripur Pandua (Retrofit) PWSS 2. Digsui Heora Z-I (Retrofit) PWSS 3. Digsui Heora Z-II (Retrofit) PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000835/2023-2024 | 213/CH | 29/02/2024 | 07/03/2024 | MAA BUNAMATA ENTERPRISE | 0.48 | 0 | 0 | 45
14 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Quotation money deposition for new service connection at Sripur w/s scheme, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004132708 Reference ID- 503625865 SM Code- 13411 |  |  | BILL/00326/2024-2025 | 104 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.47 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-3 of Sripur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001916/2024-2025 | 267/CH | 20/02/2025 | 02/03/2025 | ASHA ENTERPRISE | 1.66 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/13411 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Sripur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001885/2024-2025 | 246/CH | 19/02/2025 | 01/03/2025 | ASHA ENTERPRISE | 2.73 | 0 | 0 | 0
Total | [13 empty] | 169.89 | 0 | 0