## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Pursura | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13501 | New | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 1386/43/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 3.73 | 0 | 0 | 0
2 | HOOGHLY | Pursura | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13501 | New | Material Requisition To Resource Division |  |  | RTOR000452/2023-2024 | 3057/23/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 3.73 | 0 | 0 | 0
3 | HOOGHLY | Pursura | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13501 | New | Material Requisition To Resource Division |  |  | RTOR000238/2022-2023 | 127/26/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 19.18 | 0 | 0 | 0
4 | HOOGHLY | Pursura | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13501 | New | Material Requisition To Resource Division |  |  | RTOR000331/2023-2024 | 2607/2/Hug | 29/08/2023 | 29/08/2023 | Resource Division | 2.97 | 0 | 0 | 0
5 | HOOGHLY | Pursura | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13501 | New | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 1263/5/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 18.83 | 0 | 0 | 0
6 | HOOGHLY | Pursura | Electrical | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13501 | New | Quotation Bill for New Service Connection at Sahapur W/S. Sch. TW-II |  |  | BILL/03830/2023-2024 | 288 | 20/09/2023 | 20/09/2023 | WBSEDCL | 7.41 | 0 | 0 | 0
7 | HOOGHLY | Pursura | Electrical | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13501 | New | Quotation Bill for New Service Connection at Sahapur W/S. Sch. TW-I |  |  | BILL/03829/2023-2024 | 287 | 20/09/2023 | 20/09/2023 | WBSEDCL | 5.55 | 0 | 0 | 0
8 | HOOGHLY | Pursura | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13501 | New | SAHAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000741/2022-2023 | 617/HUG | 03/03/2023 | 28/11/2023 | M/S RAJKUMAR KHAN | 266.71 | 249.15 | 93.42 | 80
9 | HOOGHLY | Pursura | Electrical | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/13501 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sahapur water supply scheme TW No I and II Block Pursurah, District Hooghly under ED PHED. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1,Junior Engineer3 | ORD/000233/2022-2023 | 864/ED | 14/02/2023 | 15/05/2023 | TRIO CONCERN | 20.77 | 20.76 | 99.95 | 45
Total | [13 empty] | 348.88 | 269.91 | 77.37