## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat - II | Electrical | Kapsit Mini Piped Water Supply Scheme | SM/13554 | New | Supply & Delivery of standby submersible pumping machinery for Kapsit & others W/S. Sch. |  |  | ORD/001120/2021-2022 | 556/HMSD | 17/03/2022 | 15/06/2022 | DITHI ENTERPRISE | 0.79 | 0 | 0 | 0
2 | HOOGHLY | Goghat - II | Hooghly Division | Kapsit Mini Piped Water Supply Scheme | SM/13554 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  |  | BILL/00086/2022-2023 | null | 27/12/2022 |  | DISTRICT MAGISTRATE HOOGHLY | 26.6 | 0 | 0 | 0
3 | HOOGHLY | Goghat - II | Hooghly Division | Kapsit Mini Piped Water Supply Scheme | SM/13554 | New | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 1385/46/Hug | 15/05/2023 |  | Resource Division | 0.33 | 0 | 0 | 0
4 | HOOGHLY | Goghat - II | Hooghly Division | Kapsit Mini Piped Water Supply Scheme | SM/13554 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00221/2023-2024 | null | 23/06/2023 |  | DISTRICT MAGISTRATE HOOGHLY | 29.55 | 0 | 0 | 0
5 | HOOGHLY | Goghat - II | Hooghly Division | Kapsit Mini Piped Water Supply Scheme | SM/13554 | New | MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00418/2023-2024 | BP-2023-24-343 | 31/08/2023 |  | DISTRICT MAGISTRATE HOOGHLY | 28.37 | 0 | 0 | 0
6 | HOOGHLY | Goghat - II | Hooghly Division | Kapsit Mini Piped Water Supply Scheme | SM/13554 | New | MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00418/2023-2024 | BP-2023-24-343 | 31/08/2023 |  | DISTRICT MAGISTRATE HOOGHLY | 28.37 | 0 | 0 | 0
7 | HOOGHLY | Goghat - II | Electrical | Kapsit Mini Piped Water Supply Scheme | SM/13554 | New | Mini Piped Water Supply Scheme |  |  | BILL/01598/2024-2025 | null | 05/08/2024 |  | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
8 | HOOGHLY | Goghat - II | Electrical | Kapsit Mini Piped Water Supply Scheme | SM/13554 | New | Mini Piped water Supply Scheme |  |  | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 |  | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
Total | [13 empty] | 479.25 | 0 | 0