## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Balagarh | Hooghly Division | Rampur Mini Piped Water Supply Scheme | SM/13563 | New | Material Requisition To Resource Division |  |  | RTOR000236/2023-2024 | 1386/15/Hug | 15/05/2023 |  | Resource Division | 0.58 | 0 | 0 | 0
2 | HOOGHLY | Balagarh | Hooghly Division | Rampur Mini Piped Water Supply Scheme | SM/13563 | New | MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00359/2023-2024 | BP-2023-24-299 | 19/08/2023 |  | DISTRICT MAGISTRATE HOOGHLY | 31.91 | 0 | 0 | 0
3 | HOOGHLY | Balagarh | Hooghly Division | Rampur Mini Piped Water Supply Scheme | SM/13563 | New | MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00359/2023-2024 | BP-2023-24-299 | 19/08/2023 |  | DISTRICT MAGISTRATE HOOGHLY | 31.91 | 0 | 0 | 0
4 | HOOGHLY | Balagarh | Hooghly Division | Rampur Mini Piped Water Supply Scheme | SM/13563 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Muragari Mini PWSS 2. Charsundalpur Mini PWSS 3. Digra Mini PWSS 4. Rampur Mini PWSS 5. Naopara Mini PWSS 6. Telinipara Mini PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000831/2023-2024 | 209/CH | 29/02/2024 | 07/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 45
5 | HOOGHLY | Balagarh | Electrical | Rampur Mini Piped Water Supply Scheme | SM/13563 | New | Mini piped Water Supply scheme |  |  | BILL/01597/2024-2025 | BILL/01597/2024 | 16/08/2024 |  | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
Total | [13 empty] | 354.15 | 0 | 0