## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Tarakeswar | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME | SM/13568 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 1235/15/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 47.05 | 0 | 0 | 0
2 | HOOGHLY | Tarakeswar | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME | SM/13568 | New | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 1383/2/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 16.44 | 0 | 0 | 0
3 | HOOGHLY | Tarakeswar | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME | SM/13568 | New | Material Requisition To Resource Division |  |  | RTOR000388/2023-2024 | 3058/24/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.55 | 0 | 0 | 0
4 | HOOGHLY | Tarakeswar | Electrical | BINAGRAM PIPED WATER SUPPLY SCHEME | SM/13568 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Binagram water supply scheme, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer2 | ORD/000183/2022-2023 | 776/ED | 09/02/2023 | 10/05/2023 | STANDARD ELECTRICALS | 22.4 | 0 | 0 | 50
5 | HOOGHLY | Tarakeswar | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME | SM/13568 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Binagram 1st T/W site & Naita 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000283/2024-2025 | 922/Chan | 19/07/2024 | 03/08/2024 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
6 | HOOGHLY | Tarakeswar | Electrical | BINAGRAM PIPED WATER SUPPLY SCHEME | SM/13568 | New | Quotation Bill for New Service Connection at Binogram W/S. Sch. PH-I |  |  | BILL/04607/2023-2024 | 606 | 03/01/2024 | 03/01/2024 | WBSEDCL | 7.72 | 0 | 0 | 0
7 | HOOGHLY | Tarakeswar | Electrical | BINAGRAM PIPED WATER SUPPLY SCHEME | SM/13568 | New | Quotation Bill for New Service Connection at Binogram W/S. Sch. PH-II |  |  | BILL/04599/2023-2024 | 605 | 03/01/2024 | 03/01/2024 | WBSEDCL | 20.72 | 0 | 0 | 0
8 | HOOGHLY | Tarakeswar | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME | SM/13568 | New | BINAGRAM Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | ORD/000264/2023-2024 | 2238/HUG | 01/08/2023 | 03/02/2025 | SIBSANKAR CHOWDHURY | 672.18 | 0 | 0 | 30
Total | [13 empty] | 802.03 | 0 | 0