## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat - I | Hooghly Division | Adra mini pipe water supply scheme | SM/13589 | New | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 1385/48/Hug | 15/05/2023 |  | Resource Division | 0.56 | 0 | 0 | 0
2 | HOOGHLY | Goghat - I | Hooghly Division | Adra mini pipe water supply scheme | SM/13589 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00289/2023-2024 | BP-2023-24-240 | 02/08/2023 |  | DISTRICT MAGISTRATE HOOGHLY | 32.72 | 0 | 0 | 0
3 | HOOGHLY | Goghat - I | Hooghly Division | Adra mini pipe water supply scheme | SM/13589 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00289/2023-2024 | BP-2023-24-240 | 02/08/2023 |  | DISTRICT MAGISTRATE HOOGHLY | 32.72 | 0 | 0 | 0
4 | HOOGHLY | Goghat - I | Electrical | Adra mini pipe water supply scheme | SM/13589 | New | Mini Piped Water Supply Scheme. |  |  | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 |  | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
Total | [13 empty] | 159.43 | 0 | 0