## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Balagarh | Hooghly Division | Telinipara Mini Piped Water Supply Scheme | SM/13599 | New | MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00360/2023-2024 | BP-2023-24-300 | 19/08/2023 | 19/08/2023 | DISTRICT MAGISTRATE HOOGHLY | 29.33 | 0 | 0 | 0
2 | HOOGHLY | Balagarh | Electrical | Telinipara Mini Piped Water Supply Scheme | SM/13599 | New | Mini piped Water Supply scheme |  |  | BILL/01597/2024-2025 |  | 05/08/2024 | 05/08/2024 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
3 | HOOGHLY | Balagarh | Electrical | Telinipara Mini Piped Water Supply Scheme | SM/13599 | New | Mini Piped Water Supply Scheme |  |  | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 01/10/2024 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
Total | [13 empty] | 394.57 | 0 | 0