## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | Purba Chakla Mini Piped Water Supply Scheme | SM/13666 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  |  | BILL/00088/2022-2023 |  | 27/12/2022 | 27/12/2022 | DISTRICT MAGISTRATE HOOGHLY | 28.42 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | Purba Chakla Mini Piped Water Supply Scheme | SM/13666 | New | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 1385/5/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 0.46 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Hooghly Division | Purba Chakla Mini Piped Water Supply Scheme | SM/13666 | New | MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00415/2023-2024 | BP-2023-24-340 | 31/08/2023 | 31/08/2023 | DISTRICT MAGISTRATE HOOGHLY | 30.2 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Hooghly Division | Purba Chakla Mini Piped Water Supply Scheme | SM/13666 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00218/2023-2024 |  | 23/06/2023 | 23/06/2023 | DISTRICT MAGISTRATE HOOGHLY | 31.58 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | Purba Chakla Mini Piped Water Supply Scheme | SM/13666 | New | Mini Piped water Supply Scheme |  |  | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 16/08/2024 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
Total | [13 empty] | 379.46 | 0 | 0