## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Construction of 1 no.150 CUM capacity R.C.C. Elevated Reservoir with 20 m staging height Over R.C.C Bored Pile Foundation/Raft Foundation as per Departmental Type Drawing Design and Specification including pipeline connection and cost of pipes, specials alongwith Laying Distribution System & Construction of 5.4 M X3.65 M Switch Room with Additional Plinth Height, Sanitary and Water Supply Arrangements including Soil Investigation works for construction of OHR at Head Work Site for BHANDARHATI W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer,Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000125/2021-2022 | 1143/Hug | 29/06/2021 | 29/04/2022 | UNIQUE AGENCY | 117.52 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at BHANDARHATI (1NO.), PURBA THAKURANI CHAK (2NOS.), HARISH CHAK (2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer |  | ORD/000591/2023-2024 | 3268/HUG | 08/11/2023 | 07/01/2024 | KRISHNA MONDAL | 58.98 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHANDARHATI (1NO.),PURBA THAKURANI CHAK( 2NOS.), HARISH CHAK( 2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000644/2023-2024 | 3474/HUG | 29/11/2023 | 13/01/2024 | CIVIL CRAFT | 88.67 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Preparation of DPR for Augmentation of Bhanderhati Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000460/2021-2022 | 66/CH | 27/01/2022 | 03/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.77 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Additional Survey work for Preparation of DPR for Augmentation of Bhanderhati Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000461/2021-2022 | 67/CH | 27/01/2022 | 03/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.35 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Construction of approach road at Head work Site of BHANDARHATI Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E.Dte. [Block - Arambagh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000430/2022-2023 | 734/Arg | 29/09/2022 | 14/10/2022 | UNIQUE AGENCY | 3.67 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Laying of pipe line for left out portion within command area of Samta, Dakshin Para, Kazi Para, Paschim Para habitation of Samta Village, Tnaksal, Dakshin Para habitation of Takshal Village & Balaichak, Kaji Para habitation of Balai Chak Village under BHANDARHATI Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block - Arambagh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000431/2022-2023 | 736/Arg | 29/09/2022 | 24/10/2022 | UNIQUE AGENCY | 1.59 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000226/2022-2023 | 226/3/Hug | 24/01/2023 | 24/01/2023 | Resource Division | 60.58 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000258/2023-2024 | 1386/37/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 22.62 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | "Quotation Bill for New Service Connection at Bhandarhati W/S. Sch. TW-III" |  |  | BILL/03757/2023-2024 | 253 | 05/09/2023 | 05/09/2023 | WBSEDCL | 6.25 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Quotation for new service connection charge at Bhanderhati PWSS, TW - IV |  |  | BILL/04368/2023-2024 | 453 | 01/12/2023 | 01/12/2023 | WBSEDCL | 4.22 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | "Quotation Bill for New Service Connection at Bhandarhati TW-III" |  |  | BILL/03791/2023-2024 | 311 | 29/09/2023 | 29/09/2023 | WBSEDCL | 0.11 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Quotation Bill for New Service Connection at Bhandarhati TW-III |  |  | BILL/03789/2023-2024 |  | 11/09/2023 | 11/09/2023 | WBSEDCL | 6.36 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Laying C.I/D.I pipes & specials for rising main pipe line in between T.W No. -I & II to O.H.R and interconnection with distribution system including allied work of BHANDARHATI W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000130/2022-2023 | 441/Arg | 22/06/2022 | 22/07/2022 | UNIQUE AGENCY | 3.93 | 0 | 0 | 99
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in DASGHARA II GP of DHANIAKHALI Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000917/2023-2024 | 252/CH | 12/03/2024 | 11/04/2024 | TOTON MONDAL | 4.99 | 0 | 0 | 90
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR CHINSURAH DHANIAKHALI |  |  | BILL/00660/2024-2025 | BP-2024-25-499 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 18.03 | 0 | 0 | 0
17 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Quotation of New Service Connection for Bhandarhati w/s Scheme,PH No-V, Block-Dhaniakhali Dist-Hooghly under electrical division,PHE Dte.(SM/14040)Application No-5004059159 Reference Id-503589837. |  |  | BILL/00325/2024-2025 | 97 | 06/05/2024 | 06/05/2024 | WBSEDCL | 10.74 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FORHARIPAL DHANIAKHALI ROAD |  |  | BILL/00661/2024-2025 | BP-2024-25-499 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 45.52 | 0 | 0 | 0
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Electric quot. of WBSEDCL for Bhanderhati T/W-V W/S scheme under ED PHE Dte. (SM/14040) |  |  | BILL/01163/2024-2025 | 291 | 15/07/2024 | 15/07/2024 | WBSEDCL | 1.77 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Quotation for New Service Connection at Bhandarhati W/S. Sch. TW-I |  |  | BILL/04659/2023-2024 | 667 | 15/01/2024 | 15/01/2024 | WBSEDCL | 8.52 | 0 | 0 | 0
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR HARIPAL BHANDARHATI ROAD |  |  | BILL/00659/2024-2025 | BP-2024-25-499 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 13.02 | 0 | 0 | 0
22 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhandarhati water supply scheme, T.W. No.- I, II, III & IV, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000201/2022-2023 | 828/ED | 14/02/2023 | 15/03/2025 | EASTERN INDIA SALES & SERVICE | 42.97 | 0 | 0 | 25
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | BHANDARHATI ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr.Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under DHANIAKHALI Block under Chinsurah Sub-Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000093/2023-2024 | 1357/HUG | 12/05/2023 | 31/08/2025 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 302.26 | 0 | 0 | 50
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | Sinking of Tube Well, Rising Main, Construction of switch-room & boundary wall at Proposed TW site, Repairing of Switch Room & Boundary wall, Repairing of OHR in Zone-I & FHTC within Zone-I & II For Augmentation of BHANDARHATI ZONE-I &II Piped Water Supply Scheme under DHANIAKHALI Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000781/2022-2023 | 845/HUG | 23/03/2023 | 24/09/2025 | DAS ENTERPRISE | 184.79 | 0 | 0 | 85
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | SM/14040 | Augmentation | BHANDARHATI ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of switch-room & boundary wall at Proposed TW site under DHANIAKHALI Block under Chinsruah Sub-Division of Hooghly Division, PHE Dte. District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000003/2023-2024 | 1011/HUG | 06/04/2023 | 30/04/2025 | M/S S.G. CONSTRUCTION | 247.48 | 0 | 0 | 99
Total | [13 empty] | 1259.69 | 0 | 0