## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14116 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahisgot water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-I District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000176/2022-2023 | 769/ED | 09/02/2023 | 10/05/2023 | M/S S R ENTERPRISE | 20.27 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14116 | New | Material Requisition To Resource Division |  |  | RTOR000488/2023-2024 | 3057/4/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 12.4 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14116 | New | Material Requisition To Resource Division |  |  | RTOR000217/2022-2023 | 127/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 35.96 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14116 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MAHISHGOT Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000301/2024-2025 | 3659/HUG | 13/11/2024 | 11/02/2025 | MAA BUNAMATA ENTERPRISE | 16.12 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14116 | New | Quotation of New Service Connection for Mahisgot w/s Scheme,Zone-II,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/14116) Application No-5004015913 Reference Id-503563370 |  |  | BILL/06067/2023-2024 | 755 | 16/02/2024 | 16/02/2024 | WBSEDCL | 5.89 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14116 | New | Quotation of New Service Connection for Mahisgot w/S Scheme,Zone-II,PH No-II Block-Khanakul-I Dist-Hooghly under ED,PHE Dte. (SM/14116) Application No-5004068599 Reference Id-503594190 |  |  | BILL/06468/2023-2024 | 892 | 18/03/2024 | 18/03/2024 | WBSEDCL | 4.28 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14116 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 01/01/2026 | MACKINTOSH BURN LIMITED | 3480.01 | 301.94 | 8.68 | 45
8 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14116 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. |  |  | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 06/04/2025 | TECHVISION | 14.8 | 0 | 0 | 0
Total | [13 empty] | 3589.73 | 301.94 | 8.41