## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14117 | New | RADHABALLAVPUR (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls at different TW site under KHANAKUL-I Block, District- Hooghly.[NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000779/2022-2023 | 833/HUG | 22/03/2023 | 01/07/2025 | M/S S.G. CONSTRUCTION | 364.99 | 274.46 | 75.2 | 80
2 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14117 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Radhaballavpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-I District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000180/2022-2023 | 773/ED | 09/02/2023 | 01/05/2025 | KARTICK BAL | 20.62 | 15.73 | 76.27 | 30
3 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14117 | New | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 1385/23/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 9.95 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14117 | New | Material Requisition To Resource Division |  |  | RTOR000403/2023-2024 | 3057/49/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 9.95 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14117 | New | Material Requisition To Resource Division |  |  | RTOR000224/2022-2023 | 127/22/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 20.88 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14117 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 1234/37/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 11.79 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14117 | New | Quotation for new service connection charge at Radhaballavpur PWSS, Zone-II, TW - II |  |  | BILL/04484/2023-2024 | 530 | 15/12/2023 | 15/12/2023 | WBSEDCL | 13 | 0 | 0 | 0
8 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/14117 | New | Quotation for new service connection charge at Radhaballavpur PWSS, Zone-II, TW - I |  |  | BILL/04365/2023-2024 | 459 | 01/12/2023 | 01/12/2023 | WBSEDCL | 6.9 | 0 | 0 | 0
Total | [13 empty] | 458.08 | 290.19 | 63.35