## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Polba-Dadpur | Electrical | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001215/2022-2023 | 3490 / ED | 30/12/2022 | 30/03/2023 | P.K. ENGINEERING | 20.24 | 0 | 0 | 98
2 | HOOGHLY | Polba-Dadpur | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | Material Requisition To Resource Division |  |  | RTOR000255/2023-2024 | 1386/34/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 4.92 | 0 | 0 | 0
3 | HOOGHLY | Polba-Dadpur | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | Material Requisition To Resource Division |  |  | RTOR000535/2023-2024 | 3059/4/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 6.06 | 0 | 0 | 0
4 | HOOGHLY | Polba-Dadpur | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | Material Requisition To Resource Division |  |  | RTOR000164/2022-2023 | 1264/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 10.79 | 0 | 0 | 0
5 | HOOGHLY | Polba-Dadpur | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHINSURAH SUB-DIVISION, PHE DTE. UNDER HOOGHLY DIVISION, PHE DTE. |  |  | BILL/00107/2023-2024 | BP-2023-24-106 | 02/06/2023 | 02/06/2023 | PRASUN ENTERPRISE (PRASUN BISWAS) | 3.59 | 0 | 0 | 0
6 | HOOGHLY | Polba-Dadpur | Electrical | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | Quotation for new service connection at Haripur W/S Sch., T/W No. - II, Block - Polba-dadpur, Dist. - Hooghly |  |  | BILL/02328/2023-2024 | 147 | 26/07/2023 | 26/07/2023 | WBSEDCL | 2.9 | 0 | 0 | 0
7 | HOOGHLY | Polba-Dadpur | Electrical | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | Quotation for new service Connection at Haripur W/S Sch., T/W No. - I, Block - Polba-Dadpur, District - Hooghly |  |  | BILL/03711/2023-2024 | 252 | 05/09/2023 | 05/09/2023 | WBSEDCL | 5.79 | 0 | 0 | 0
8 | HOOGHLY | Polba-Dadpur | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | HARIPUR Piped Water Supply Scheme with Sinking of tube-well, Laying Distribution System, Rising Main, Providing FHTC, construction of switch-rooms & boundary walls at different TW site under Hooghly Division, PHE Dte. within POLBA-DADPUR Block, District-Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000700/2022-2023 | 363/HUG | 08/02/2023 | 09/05/2023 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 183.69 | 0 | 0 | 95
9 | HOOGHLY | Polba-Dadpur | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Rudrani PWSS 2. Chalua PWSS 3. Kamrai PWSS 4. Haripur PWSS 5. Kumrul PWSS 6. Kuchpala PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000775/2023-2024 | 141/CH | 20/02/2024 | 27/02/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 30
10 | HOOGHLY | Polba-Dadpur | Electrical | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/14122 | New | Quotation for new service connection at Haripur W/S Sch.[SM/14122], Block - Polba-Dadpur, WBSEDCL, Ref. Id. - 503619164, Dt. - 25/04/2024, Application No. - 5004117110 |  |  | BILL/00475/2024-2025 | 135 | 17/05/2024 | 17/05/2024 | WBSEDCL | 4.71 | 0 | 0 | 0
Total | [13 empty] | 243.63 | 0 | 0