## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Material Requisition To Resource Division |  |  | RTOR000239/2023-2024 | 1386/18/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 31.19 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Material Requisition To Resource Division |  |  | RTOR000508/2023-2024 | 3059/13/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 31.19 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 1264/21/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 33.14 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Electrical | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dashghara water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/000252/2022-2023 | 919/ED | 22/02/2023 | 23/05/2023 | H.K.DAS & CO. | 43.01 | 0 | 0 | 35
5 | HOOGHLY | Dhaniakhali | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BISHNUPUR, DASHGHARA ZONE-I, DASHGHARA ZONE-II (1NO.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000323/2023-2024 | 2407/HUG | 11/08/2023 | 25/09/2023 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 0 | 0 | 40
6 | HOOGHLY | Dhaniakhali | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000325/2023-2024 | 2408/HUG | 11/08/2023 | 25/09/2023 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 0 | 0 | 20
7 | HOOGHLY | Dhaniakhali | Electrical | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Quotation Bill for New Service Connection at Dashghara W/S. Sch. TW-I |  |  | BILL/05345/2023-2024 | 701 | 22/01/2024 | 22/01/2024 | WBSEDCL | 12.21 | 0 | 0 | 0
8 | HOOGHLY | Dhaniakhali | Electrical | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Quotation Bill for New Service Connection at Dhasghara W/S. Sch. Z-I, TW-II & Z-ii, TW-I |  |  | BILL/04947/2023-2024 | 676 & 677 | 18/01/2024 | 18/01/2024 | WBSEDCL | 12.17 | 0 | 0 | 0
9 | HOOGHLY | Dhaniakhali | Electrical | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Quotation Bill for New Service Connection at Dashghara W/S. Sch. TW-II |  |  | BILL/05358/2023-2024 | 700 | 22/01/2024 | 22/01/2024 | WBSEDCL | 9.7 | 0 | 0 | 0
10 | HOOGHLY | Dhaniakhali | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2023-2024 | 2066/HUG | 17/07/2023 | 02/08/2025 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 0 | 0 | 20
11 | HOOGHLY | Dhaniakhali | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Dasghara (Zone-II) Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000333/2023-2024 | 2417/HUG | 11/08/2023 | 22/03/2025 | GEE BEE NIRMAN CO PRIVATE LIMITED | 52.06 | 0 | 0 | 30
12 | HOOGHLY | Dhaniakhali | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/14531 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Dasghara (Zone-I) Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000332/2023-2024 | 2416/HUG | 11/08/2023 | 22/03/2025 | GEE BEE NIRMAN CO PRIVATE LIMITED | 53.78 | 0 | 0 | 28
Total | [13 empty] | 2697.59 | 0 | 0