## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 1385/39/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 4.96 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Material Requisition To Resource Division |  |  | RTOR000428/2023-2024 | 3057/36/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 4.96 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Additional Quotation for Shantipur w/s Scheme,Zone-II,PH no-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte,(SM/14684) Application No-100000124534 Reference Id-860319604 |  |  | BILL/02603/2024-2025 | 636 | 18/12/2024 | 18/12/2024 | WBSEDCL | 0.91 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Quotation of New service Connection at Shantipur w/s Scheme,Zone-II,PH No-II Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/14684) Application No-5004136393 Reference Id-503627261. |  |  | BILL/00327/2024-2025 | 96 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.39 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Quotation App. No.-5004182874 SM/14684 |  |  | BILL/00466/2024-2025 | 117 | 17/05/2024 | 17/05/2024 | WBSEDCL | 13.85 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shantipur water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000182/2022-2023 | 775/ED | 09/02/2023 | 01/11/2025 | A.G. ENTERPRISE | 20.26 | 0 | 0 | 40
7 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 01/07/2025 | M/S PRITI ENTERPRISE | 4251.5 | 0 | 0 | 30
Total | [13 empty] | 4299.83 | 0 | 0