## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 1385/39/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 4.96 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Material Requisition To Resource Division |  |  | RTOR000428/2023-2024 | 3057/36/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 4.96 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Additional Quotation for Shantipur w/s Scheme,Zone-II,PH no-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte,(SM/14684) Application No-100000124534 Reference Id-860319604 |  |  | BILL/02603/2024-2025 | 636 | 18/12/2024 | 18/12/2024 | WBSEDCL | 0.91 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Quotation of New service Connection at Shantipur w/s Scheme,Zone-II,PH No-II Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/14684) Application No-5004136393 Reference Id-503627261. |  |  | BILL/00327/2024-2025 | 96 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.39 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Quotation App. No.-5004182874 SM/14684 |  |  | BILL/00466/2024-2025 | 117 | 17/05/2024 | 17/05/2024 | WBSEDCL | 13.85 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shantipur water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000182/2022-2023 | 775/ED | 09/02/2023 | 01/11/2025 | A.G. ENTERPRISE | 20.26 | 0 | 0 | 40
7 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 01/07/2025 | M/S PRITI ENTERPRISE | 4251.5 | 120.14 | 2.83 | 30
8 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/14684 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. |  |  | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 22/03/2025 | TECHVISION | 6.59 | 0 | 0 | 0
Total | [13 empty] | 4306.42 | 120.14 | 2.79