## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1234/30/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 25.45 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Material Requisition To Resource Division |  |  | RTOR000493/2023-2024 | 3057/60/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 13.4 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selampur water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000181/2022-2023 | 774/ED | 09/02/2023 | 01/10/2025 | S S ENTERPRISES | 22.09 | 0 | 0 | 10
4 | HOOGHLY | Goghat-II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034199 Reference Id-503574970 |  |  | BILL/06202/2023-2024 | 809 | 28/02/2024 | 28/02/2024 | WBSEDCL | 4.48 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Quotation of New Service Connection For Selampur w/s Scheme,Zone-II,PH No-III Block-Goghat-II Dist-Hooghly under Electrical division,PHE Dte.(SM/14685) Application No-5004431262 Reference Id-503764740 |  |  | BILL/02058/2024-2025 | 537 | 28/10/2024 | 28/10/2024 | WBSEDCL | 4.39 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-II Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034192 Reference Id-503574969. |  |  | BILL/06201/2023-2024 | 810 | 28/02/2024 | 28/02/2024 | WBSEDCL | 4.41 | 0 | 0 | 0
7 | HOOGHLY | Goghat-II | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 01/07/2025 | M/S PRITI ENTERPRISE | 4251.5 | 0 | 0 | 30
8 | HOOGHLY | Goghat-II | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000847/2023-2024 | 725/HUG | 05/03/2024 | 01/01/2026 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 0 | 0 | 70
9 | HOOGHLY | Goghat-II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELAMPUR PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000140/2024-2025 | 1166/ED | 14/06/2024 | 01/10/2025 | S.S. ENTERPRISES | 10.95 | 0 | 0 | 0
10 | HOOGHLY | Goghat-II | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 22/03/2025 | TECHVISION | 6.59 | 0 | 0 | 0
Total | [13 empty] | 4407.59 | 0 | 0