## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-I | Electrical | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000173/2022-2023 | 766/ED | 09/02/2023 | 10/05/2023 | BARISAL TRADING CO. | 20.5 | 0 | 0 | 0
2 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement ,Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of GOBINDANAGAR ZONE-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000360/2023-2024 | 2452/HUG | 12/08/2023 | 11/10/2023 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 16.55 | 0 | 0 | 0
3 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 1385/32/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 11.27 | 0 | 0 | 0
4 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Material Requisition To Resource Division |  |  | RTOR000418/2023-2024 | 3057/41/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 11.27 | 0 | 0 | 0
5 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1234/23/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 70.25 | 0 | 0 | 0
6 | HOOGHLY | Goghat-I | Electrical | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Quotation of new Service Connection for Gobindanagar Water supply Scheme,Zone-II,PH No-I Block-Arambag Dist-hooghly under Electrical Division PHE Dte |  |  | BILL/04022/2023-2024 | 314 | 03/10/2023 | 03/10/2023 | WBSEDCL | 4.73 | 0 | 0 | 0
7 | HOOGHLY | Goghat-I | Electrical | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-II, T.W. No. III, Block: Goghat-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002472/2023-2024 | 333/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
8 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | GOBINDANAGAR (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000052/2023-2024 | 1520/HUG | 23/05/2023 | 01/01/2026 | BAPPADITYA BANERJEE | 500 | 295.72 | 59.14 | 20
9 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GOBINDANAGAR (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000811/2023-2024 | 595/HUG | 22/02/2024 | 21/03/2025 | BAPPADITYA BANERJEE | 31.58 | 0 | 0 | 50
10 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Additional works for Laying Distribution main by HDD process at Gopalbati and Gobindanagar Zone II W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000311/2024-2025 | 3687/HUG | 14/11/2024 | 11/10/2025 | MS PRADIP KUMAR PAL | 14.33 | 0 | 0 | 0
11 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | ROAD RESTORATION PAYMENT TO PWD FOR GOGHAT RAMJIBONPUR MORE ROAD |  |  | BILL/00671/2024-2025 | BP-2024-25-500 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 8.23 | 0 | 0 | 0
12 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Quotation of New Service Connection for Gobindanagar w/s scheme,Zone-II,PH No-III Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/14982) Application No-5004564161,Reference Id-503860458 |  |  | BILL/01254/2024-2025 | C032555994400 | 18/03/2025 | 18/03/2025 | WBSEDCL | 23.22 | 0 | 0 | 0
13 | HOOGHLY | Goghat-I | Electrical | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | SM/14982 | New | Quotation of New Service Connection for Gobindanagar w/s scheme,Zone-II,PH No-II Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/14982) Application No-5004548674,Reference Id-503848464 |  |  | BILL/03087/2024-2025 | 685 | 31/01/2025 | 31/01/2025 | WBSEDCL | 3.59 | 0 | 0 | 0
Total | [13 empty] | 725.93 | 295.72 | 40.74