## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Harit water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000214/2022-2023 | 841/ED | 14/02/2023 | 15/05/2023 | DEBJYOTI BASU | 21.49 | 10.41 | 48.43 | 50
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000198/2022-2023 | 226/5/Hug | 24/01/2023 | 24/01/2023 | Resource Division | 39.48 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000276/2023-2024 | 1386/51/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 6.49 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 1264/1/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 39.48 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Augmentation of HARIT Piped Water Supply Scheme with Sinking of Tube-Well, LDS, Rising Main, FHTC, construction of switch-rooms , boundary walls& Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site under POLBA-DADPUR Block, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000701/2022-2023 | 379/HUG | 09/02/2023 | 10/05/2023 | DAS ENTERPRISE (SAMIR DAS) | 238.76 | 218.37 | 91.46 | 92
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in HARIT GP of POLBA-DADPUR Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000924/2023-2024 | 244/CH | 12/03/2024 | 11/04/2024 | BASU & SONS | 4.98 | 4.97 | 99.75 | 75
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Providing FHTC in rest out portion of at Majher Para of Harit PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001043/2023-2024 | 287/CH | 15/03/2024 | 22/03/2024 | DAS ENTERPRISE (SAMIR DAS) | 0.99 | 0.98 | 98.9 | 85
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Providing FHTC in rest out portion of at Ichapur of Harit PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001044/2023-2024 | 288/CH | 15/03/2024 | 22/03/2024 | DAS ENTERPRISE (SAMIR DAS) | 0.82 | 0.79 | 96.58 | 95
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Providing FHTC in rest out portion of at Kelor Para of Harit PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001042/2023-2024 | 284/CH | 14/03/2024 | 21/03/2024 | DAS ENTERPRISE (SAMIR DAS) | 0.99 | 0.97 | 97.65 | 100
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Preparation of DPR for AUGMENTATION OF HARIT Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000087/2024-2025 | 689/CH | 09/08/2024 | 16/08/2024 | DULAL MAJUMDER | 3.15 | 0 | 0 | 100
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15243 | Augmentation | Repairing of Road from Dewanbheri Kachari More to Bilatpur Bridge |  |  | BILL/00360/2024-2025 | BP-2024-25-293 | 10/07/2024 | 10/07/2024 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 0.99 | 0 | 0 | 0
Total | [13 empty] | 357.62 | 236.48 | 66.13