## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-I | Electrical | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly | SM/15247 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-I, T.W. No. III & IV, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000879/2023-2024 | 3452/ED | 11/08/2023 | 09/11/2023 | PERFECT AIRCONDITION | 20.49 | 0 | 0 | 0
2 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly | SM/15247 | New | Horizontal Auger boring with water jet system Including Approach Road at GOBINDANAGAR ZONE-I, KUMURSA, KOTA, RAGHUBATI & SUNIA Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000693/2023-2024 | 3592/HUG | 05/12/2023 | 04/01/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 7.29 | 7.05 | 96.58 | 100
3 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly | SM/15247 | New | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 1385/40/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 11.06 | 0 | 0 | 0
4 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly | SM/15247 | New | Material Requisition To Resource Division |  |  | RTOR000430/2023-2024 | 3057/35/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 11.06 | 0 | 0 | 0
5 | HOOGHLY | Goghat-I | Hooghly Division | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly | SM/15247 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1234/22/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 9.97 | 0 | 0 | 0
6 | HOOGHLY | Goghat-I | Electrical | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly | SM/15247 | New | Quotation Bill for New Service Connection at Gobindanagar W/S. Sch. Z-I, PH-I |  |  | BILL/04149/2023-2024 | 393 | 03/11/2023 | 03/11/2023 | WBSEDCL | 3.97 | 0 | 0 | 0
7 | HOOGHLY | Goghat-I | Electrical | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly | SM/15247 | New | Quotation of New Service Connection for Gobindanagar w/s scheme,Zone-I,PH No-II Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/15247) Application No-5004049800, Reference Id-503584072 |  |  | BILL/06239/2023-2024 | 839 | 01/03/2024 | 01/03/2024 | WBSEDCL | 3.68 | 0 | 0 | 0
Total | [13 empty] | 67.54 | 7.05 | 10.43