## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chinsurah - Magra | Hooghly Division | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15250 | New | Material Requisition To Resource Division |  |  | RTOR000293/2023-2024 | 1386/56/Hug | 15/05/2023 |  | Resource Division | 6.75 | 0 | 0 | 0
2 | HOOGHLY | Chinsurah - Magra | Electrical | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15250 | New | Quotation for new service connection at Refaitpur W/S Sch., Zone - I, T/w No. - I, Dist. - Hooghly |  |  | BILL/03782/2023-2024 | 305 | 26/09/2023 |  | WBSEDCL | 6.1 | 0 | 0 | 0
3 | HOOGHLY | Chinsurah - Magra | Electrical | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15250 | New | Quotattion for new service connection at Refaitpur W/S Sch., Zon - I, T/W -II, Block - Chinsurah-Mogra, Dt. - Hooghly |  |  | BILL/03980/2023-2024 | 315 | 03/10/2023 |  | WBSEDCL | 13.11 | 0 | 0 | 0
4 | HOOGHLY | Chinsurah - Magra | Hooghly Division | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15250 | New | Material Requisition To Resource Division |  |  | RTOR000532/2023-2024 | 3059/34/Hug | 11/10/2023 |  | Resource Division | 6.75 | 0 | 0 | 0
5 | HOOGHLY | Chinsurah - Magra | Electrical | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15250 | New | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
6 | HOOGHLY | Chinsurah - Magra | Electrical | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15250 | New | Quotation Bill for New Service Connection at Refaitpur W/S. Sch. TW- I & II, & Z-II |  |  | BILL/04136/2023-2024 | 388&389 | 02/11/2023 |  | WBSEDCL | 11.2 | 0 | 0 | 0
7 | HOOGHLY | Chinsurah - Magra | Hooghly Division | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15250 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Gurbari PWSS 2. Lokabati PWSS 3. Bishnupur PWSS 4. Kamalpur PWSS 5. Refaitpur Z-I PWSS 6. Barul PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000773/2023-2024 | 139/CH | 20/02/2024 | 27/02/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.48 | 50 | 100
8 | HOOGHLY | Chinsurah - Magra | Hooghly Division | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15250 | New | REFAITPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHINSURAH MAGRA Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000748/2022-2023 | 684/Hug | 10/03/2023 | 05/12/2023 | SATYA NARAYAN BISWAS | 261.02 | 105.63 | 40.47 | 40
9 | HOOGHLY | Chinsurah - Magra | Electrical | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15250 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Refaitpur water supply scheme Zone I TW No I and II and Zone II TW No I and II Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000232/2022-2023 | 863/ED | 14/02/2023 | 15/05/2023 | ORIENTAL ENGINEERING CO. | 40.5 | 9.55 | 23.57 | 90
Total | [13 empty] | 435.76 | 115.65 | 26.54