## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chinsurah-Magra | Hooghly Division | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15251 | New | Material Requisition To Resource Division |  |  | RTOR000522/2023-2024 | 3059/9/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 9.67 | 0 | 0 | 0
2 | HOOGHLY | Chinsurah-Magra | Hooghly Division | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15251 | New | REFAITPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHINSURAH MAGRA Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000810/2022-2023 | 975/Hug | 31/03/2023 | 26/12/2023 | DAS ENTERPRISE (SAMIR DAS) | 244.77 | 177.94 | 72.69 | 30
3 | HOOGHLY | Chinsurah-Magra | Hooghly Division | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15251 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Dashghara PWSS 2. Patul PWSS 3. Durgapur PWSS 4. Khajurdaha PWSS 5. Refaitpur Z-II PWSS 6. Kalora PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000774/2023-2024 | 140/CH | 20/02/2024 | 27/02/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 30
4 | HOOGHLY | Chinsurah-Magra | Hooghly Division | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15251 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Refaitpur Z-II PWSS 2. Sankhangar Chakbasberia PWSS 3. Basudebbati PWSS 4. Dantra PWSS 5. Goswami Malipara PWSS 6. Amra PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000822/2023-2024 | 200/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
Total | [13 empty] | 256.35 | 179.85 | 70.16